## Master Worksheet
Task # | Stamp | Title | Description | Date | Status | Type | Sheet | Location | Created By | Assigned To | # Photos | Color | Archived | Start Date | Due Date | Cost Impact | Cost Impact Amount | Schedule Impact | Schedule Impact Amount (days) | List | Last Updated | Closed On
1 | 1P | Priority 1: Parking | The van accessible parking space and access aisle have a running slope of up to 3.3% and has some cracking and gaps in the asphalt. Recommendation: Replace asphalt surface at parking space and access aisle. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 3500 |  |  |  | Oct 14, 2019 @ 17:03
3 | 1P | Priority 1: Parking | The three easternmost accessible parking spaces have cracking and gaps in the asphalt, and the easternmost accessible parking space has a running slope of up to 2.8%. Recommendation: Replace asphalt surface at parking spaces and access aisles. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 7000 |  |  |  | Oct 14, 2019 @ 16:39
4 | 1A | Priority 1: Accessible Routes | The route from the van accessible parking space to the public sidewalk has an approximate 1" wide gap. Recommendation: Fill gap with caulking material. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:38
5 | 1A | Priority 1: Accessible Routes | The route from the easternmost accessible parking spaces to the public sidewalk has two approximately 1" wide gaps. Recommendation: Fill gaps with caulking material. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:38
6 | 1A | Priority 1: Accessible Routes | The route from the two center accessible parking spaces to the public sidewalk has two approximately 1" wide gaps. Recommendation: Fill gaps with caulking material. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:38
7 | 1R | Priority 1: Ramps | The ramp at the south entrance has the following issues: 1) Excessive gaps surrounding the bottom landing 2) Missing handrail extension on one side of the top and bottom landings 3) Intermediate landing is less than 60" x 60" clear 4) Upper landing has a cross slope of approximately 2.8% Recommendation: Remove and replace ramp. | May 11, 2021 @ 19:00 | open | Issue | C3 | Route to South Entrance | kgoss@abyd.com | 0 | 12 | red | No | 0 | 0 | Yes | 7500 |  |  |  | Oct 14, 2019 @ 16:34
8 | 1E | Priority 1: Entrances | The door maneuvering area on the pull side of the entrance doors has a running slope of approximately 3.1%. Recommendation: Replace landing area at door and stair. | May 11, 2021 @ 19:00 | open | Issue | C3 | South Entrance | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 12500 |  |  |  | Oct 14, 2019 @ 16:38
9 | 1P | Priority 1: Parking | Both accessible parking spaces and the shared access aisle have excessive cross slopes ranging from 3.3% to 3.9%. Recommendation: Replace asphalt surface at parking spaces. | May 11, 2021 @ 19:00 | open | Issue | C2 | North Parking Lot | kgoss@abyd.com | 0 | 9 | red | No | 0 | 0 | Yes | 6500 |  |  |  | Oct 14, 2019 @ 16:36
10 | 1A | Priority 1: Accessible Routes | The base of the curb ramp has a change in level of approximately 1/2". Recommendation: Grind the edge to create a maximum 1:2 bevel. | May 11, 2021 @ 19:00 | open | Issue | C2 | Route from South Accessible Parking | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:34
12 | 2H | Priority 2: Reach Range | The shelf above the clothes rod is 51-1/2" high. Recommendation: Lower a portion of rod and shelf to a maximum height of 48". (Note: If this shelf was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 11, 2021 @ 19:00 | open | Issue | A1 | Women's Dressing Room | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:36
14 | 2P | Priority 2: Protruding Objects | A series of panels and equipment boxes project more than 4" from the wall between 27" and 80" high. Recommendation: Add cane detection railing below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Backstage Vestibule | kgoss@abyd.com | 0 | 8 | red | No | 0 | 0 | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:35
15 | 2P | Priority 2: Protruding Objects | The panel box near the ballroom projects more than 4" from the wall between 27" and 80" high. Recommendation: Add cane detection railing below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Loading Dock Corridor | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:37
16 | 2R | Priority 2: Ramps | The ramp to the stage has the following noncompliant conditions: 1) The slope of both runs are approximately 8.5%; however, it may be considered within reasonable construction tolerance 2) The bottom landing has an approximate 1/2" high change in level 3) The intermediate landing is not 60" x 60" clear Recommendation: Remove and replace ramp. | May 11, 2021 @ 19:00 | open | Issue | A1 | Ballroom | kgoss@abyd.com | 0 | 10 | red | No | 0 | 0 | Yes | 7500 |  |  |  | Oct 14, 2019 @ 16:33
17 | 2D | Priority 2: Doors | Door vision panels in 12 doors (Exhibit Hall and Kitchen) are positioned with the bottom of the glass 56-1/4" high. Recommendation: Install doors with vision panels no higher than 43". (Note: If these doors were installed prior to March 15, 2012, they may enjoy safe harbor until they are replaced.) | May 11, 2021 @ 19:00 | open | Issue | A1 | Loading Dock Corridor | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 3000 |  |  |  | Oct 14, 2019 @ 16:57
18 | 2D | Priority 2: Doors | Door vision panels in the 5 conference room doors are positioned with the bottom of the glass more than 43" high. Recommendation: Install doors with vision panels no higher than 43". (Note: If these doors were installed prior to March 15, 2012, they may enjoy safe harbor until they are replaced.) | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 3750 |  |  |  | Oct 14, 2019 @ 16:42
19 | 3D | Priority 3: Doors | The entrance door requires more than 5 lbs of force to open. Recommendation: Adjust door closer. | May 11, 2021 @ 19:00 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 150 |  |  |  | Oct 14, 2019 @ 16:37
20 | 3D | Priority 3: Doors | The entrance door requires more than 5 lbs of force to open. Recommendation: Adjust door closer. | May 11, 2021 @ 19:00 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 150 |  |  |  | Oct 14, 2019 @ 16:37
21 | 2P | Priority 2: Protruding Objects | The Blood Control Kit and AED boxes project more than 4" from the wall at a height of 27" to 80" high. Recommendation: Add cane detection element below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com | 0 | 8 | red | No | 0 | 0 | 0 | 500 |  |  |  | Oct 14, 2019 @ 16:35
22 | 2P | Priority 2: Protruding Objects | The wall-mounted TV outside of the office entrance projects more than 4" from the wall at a height of 27" to 80". Recommendation: Add cane detection element below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:37
23 | 4V | Priority 4: Vending Machines | The two vending machines have card slides that are 50" and 58" high. Recommendation: Replace vending machines with compliant models. | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | 0 | Unspecified |  |  |  | Oct 14, 2019 @ 16:35
25 | 2K | Priority 2: Sinks | The sinks in each of the 5 conference rooms have a toe space that is only 7" high. Recommendation: Modify panel to provide a minimum 9" high toe space. | May 13, 2021 @ 14:50 | open | Issue | A1 | Conference Rooms | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 8750 |  |  |  | Oct 14, 2019 @ 16:40
26 | 2D | Priority 2: Doors | Four doors (ballroom and kitchen) do not have a smooth surface on the bottom 10" of the push side due to installed door stops. Recommendation: Remove door stops. (Note: If these doors were installed prior to March 15, 2012, they may enjoy safe harbor until they are replaced.) | May 13, 2021 @ 15:03 | open | Issue | A1 | Loading Dock Corridor | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | 0 | Unspecified |  |  |  | Oct 14, 2019 @ 16:34
27 | 2E | Priority 2: Elevators/Lifts | The platform lift to the stage has a clear width of only 34-1/2". Recommendation: Install a compliant platform lift with a minimum clear width of 36". (Note: If this lift was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:29 | open | Issue | A1 | Exhibit Hall | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 12000 |  |  |  | Oct 14, 2019 @ 16:41
28 | 3R | Priority 3: Reach Range | The openings of both paper towel dispensers are 50" and 49 1/2" high. Recommendation: Reposition at least one dispenser with opening no higher than 48". (Note: If the dispensers were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:32 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:40
29 | 3B | Priority 3: Baby Changing Stations | The surface of the baby changing table is 34-1/2" high in the open position. (Please note that TDLR considers baby changing stations to be protruding objects in their open position where the bottom of the table is more than 27" high. In this instance, the table obstructs the door maneuvering clearance in the open position.) Recommendation: Relocate baby changing station outside of the door maneuvering area and position with the top of the table 28" to 34" high in the open position. | May 14, 2021 @ 09:34 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:35
30 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is 54" high. Recommendation: Install a hook positioned no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:37 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 50 |  |  |  | Oct 14, 2019 @ 16:36
31 | 3G | Priority 3: Grab Bars | The grab bars in the wheelchair accessible toilet stall are positioned with the top of the bar 36-1/2" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. See related Item #32. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 09:39 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:36
32 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is not centered 7 to 9" in front of the water closet. Recommendation: Reposition the dispenser below the grab bar with the centerline 7" to 9" in front of the water closet. See related Item #31. (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:41 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 225 |  |  |  | Oct 14, 2019 @ 16:40
33 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:42 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 100 |  |  |  | Oct 14, 2019 @ 17:01
34 | 3W | Priority 3: Water Closets | The water closet in the wheelchair accessible toilet stall is centered approximately 18 1/2" from the side partition. Recommendation: Reposition the water closet with the centerline 16" to 18" from side wall. (Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:45 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 2500 |  |  |  | Oct 14, 2019 @ 16:42
35 | 3B | Priority 3: Baby Changing Stations | The surface of the baby changing table is 35" high in the open position. (Please note that TDLR considers baby changing stations to be protruding objects in their open position where the bottom of the table is more than 27" high.) Recommendation: Reposition the baby changing station so that the top of the table 28" to 34" high and the bottom of the table is exactly 27" in the open position. | May 14, 2021 @ 09:47 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:39
36 | 3R | Priority 3: Reach Range | The openings of both paper towel dispensers are 50" high. Recommendation: Reposition dispenser with opening no higher than 48". (Note: If the dispensers were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:47 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:41
37 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing. Recommendation: Adjust door hinges. | May 14, 2021 @ 09:48 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 225
38 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:50 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 100
39 | 3G | Priority 3: Grab Bars | The grab bars in the wheelchair accessible toilet stall are positioned with the top of the bar 37" high. Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. (Note: If the grab bars were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 09:50 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 400
40 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is 54" high. Recommendation: Install a hook positioned no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:51 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 50
41 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is 54" high. Recommendation: Install a coat hook no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:01 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 50
42 | 3R | Priority 3: Reach Range | The coat hook in the ambulatory accessible toilet stall is 54" high. Recommendation: Install a coat hook no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:01 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 50
43 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:03 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 100
44 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:03 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 100
45 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing. Recommendation: Adjust door hinge. | May 14, 2021 @ 10:04 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 225
46 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall is not self-closing. Recommendation: Adjust door hinges. | May 14, 2021 @ 10:05 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 225
47 | 3G | Priority 3: Grab Bars | The grab bars in the wheelchair accessible toilet stall are positioned with the top of the bar 36-3/4" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser. Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. See related Item #48. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 10:07 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 400
48 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is not centered 7 to 9" in front of the water closet. Recommendation: Reposition the dispenser below the grab bar with the centerline 7" to 9" in front of the water closet. See related Item #47. (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:08 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 225
49 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the ambulatory accessible toilet stall is not centered 7 to 9" in front of the water closet. Recommendation: Reposition the dispenser below the grab bar with the centerline 7" to 9" in front of the water closet. See related Item #51. (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:08 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 225 |  |  |  | Oct 14, 2019 @ 16:41
50 | 3C | Priority 3: Toilet Compartments | The side approach width to the ambulatory accessible toilet stall is only 41" wide. A minimum 42" width is required. Recommendation: Reconfigure partitions to provide a minimum 42" clearance. | May 14, 2021 @ 10:09 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 2500 |  |  |  | Oct 14, 2019 @ 16:42
51 | 3G | Priority 3: Grab Bars | The grab bars in the ambulatory accessible toilet stall are positioned 13" from the rear wall and with the top of the bar 36-3/4" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser. Recommendation: Reposition grab bars 12" from the rear wall and 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. See related Item #49. | May 14, 2021 @ 10:11 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:39
52 | 3U | Priority 3: Urinals | The accessible urinal is positioned with the rim 18-1/4" high. Recommendation: Reposition urinal with the rim no higher than 17". | May 14, 2021 @ 10:13 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 1250 |  |  |  | Oct 14, 2019 @ 16:41
53 | 3M | Priority 3: Mirrors | The mirrors over each of the lavatories are positioned with the bottom of the reflective surface 40-3/4" high. Recommendation: Reposition one mirror with the bottom of the glass no higher than 40". | May 14, 2021 @ 11:19 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 300 |  |  |  | Oct 14, 2019 @ 16:39
54 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:21 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 100 |  |  |  | Oct 14, 2019 @ 16:40
55 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:22 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 100
56 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing. Recommendation: Adjust door hinges. | May 14, 2021 @ 11:23 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 225
57 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall is not self-closing. Recommendation: Adjusts door hinges. | May 14, 2021 @ 11:24 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 225
58 | 2K | Priority 2: Sinks | The sink has a knee space height of only 25" below the sink. Recommendation: Replace sink with a shallower model. | May 14, 2021 @ 11:25 | open | Issue | A1 | Conference Kitchen | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 1000
59 | 2H | Priority 2: Reach Range | The soap dispenser is positioned with the operable part 51-3/4" high. Recommendation: Reposition dispenser with operable parts no more than 44" high. | May 14, 2021 @ 11:28 | open | Issue | A1 | Conference Kitchen | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 200
60 | 2H | Priority 2: Reach Range | The disposal switch and convenience outlets are positioned 47-3/4" high. Recommendation: Reposition the disposal switch and outlets with all operable parts and receptacles 46" high maximum. | May 14, 2021 @ 11:30 | open | Issue | A1 | Conference Kitchen | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 1000
61 | 2D | Priority 2: Doors | The door has only 17-1/2" of clearance past the strike on the pull side. Recommendation: Although the clearance is technically less than the allowable, this appears to be within reasonable tolerance. If this door is modified or replaced in the future, correction will be required. | May 14, 2021 @ 11:34 | open | Issue | A1 | Women's Dressing Room | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | 0 | Unspecified
62 | 3W | Priority 3: Water Closets | The water closet is centered approximately 18-1/4" from the side wall. Recommendation: Reposition the water closet with the centerline 16" to 18" from side wall.(Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:36 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 2500
63 | 3G | Priority 3: Grab Bars | The grab bars at the water closet are positioned with the top of the bar 36-1/2" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser Recommendation: Position grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:38 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 400
64 | 3W | Priority 3: Water Closets | The water closet has 48-1/2" of clear floor space width measured from the side wall to the edge of the lavatory. Recommendation: Enlarge restroom to allow a full 60" wide clearance at the water closet measured from side wall to edge of lavatory. (Note: If the water closet and lavatory were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:40 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 15000
65 | 3R | Priority 3: Reach Range | The opening of the paper towel dispenser is 50" high. Recommendation: Reposition dispenser with opening no higher than 48". (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:42 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 200
66 | 3E | Priority 3: Benches | The bench does not have a clear floor space at the end for a side transfer. Recommendation: Install an accessible bench with a 30x48 clear floor space at the end for side transfer. (Note: If the bench was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:43 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 2000
67 | 2H | Priority 2: Reach Range | The shelf above the clothes rod is 51-3/4" high. Recommendations: Lower a portion of rod and shelf to a maximum height of 48". (Note: If this shelf was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:45 | open | Issue | A1 | Men's Dressing Room | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 250
68 | 3E | Priority 3: Benches | The bench does not have a clear floor space at the end for a side transfer. Recommendation: Install an accessible bench with a 30x48 clear floor space at the end for side transfer. (Note: If the bench was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:47 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 2000
69 | 3W | Priority 3: Water Closets | The water closet is centered approximately 18-1/2" from the side wall. Recommendation: Reposition the water closet with the centerline 16" to 18" from side wall. (Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:49 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 2500
70 | 3G | Priority 3: Grab Bars | The grab bars at the water closet are positioned with the top of the bar 36-1/2" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:50 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 400
71 | 3W | Priority 3: Water Closets | The water closet has 48" of clear floor space width measured from the side wall to the edge of the lavatory. Recommendation: Enlarge restroom to allow a full 60" wide clearance at the water closet measured from side wall to edge of lavatory. (Note: If the water closet and lavatory were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:51 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 15000
72 | 3R | Priority 3: Reach Range | The opening of the paper towel dispenser is 50" high. Recommendation: Reposition dispenser with opening no higher than 48". (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:52 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 200
73 | 2D | Priority 2: Doors | The door has a 49" wide side approach on the pull side. Doors with closers require a minimum 54" side approach width. Recommendation: Remove door closer. | May 14, 2021 @ 11:54 | open | Issue | A1 | Men's Dressing Room | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 150
1 | 2A | Priority 2: Accessible Routes | No accessible route is provided to the bandstand. Recommendation: Install a platform lift. | May 10, 2021 @ 19:00 | open | Issue | C1 | Bandstand | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 12000
2 | 2A | Priority 2: Accessible Routes | No accessible route is provided to fountain or memorial plaques. Recommendation: Install a ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | Fountain | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 10000
4 | 1C | Priority 1: Curb Ramps | Both ramps and landing have excessive cross slopes ranging from 3.3% to 3.7%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | Northwest Curb Ramp | kgoss@abyd.com | 0 | 8 | red | No | 0 | 0 | Yes | 6000
5 | 1A | Priority 1: Accessible Routes | Entire perimeter sidewalk has cross slopes up to 5.6% and excessive changes in level. Recommendation: Remove and replace sidewalk. 584’ x 3’ (1752 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Perimeter Sidewalk | kgoss@abyd.com | 0 | 13 | red | No | 0 | 0 | Yes | 17520
6 | 1A | Priority 1: Accessible Routes | The route from the perimeter sidewalk to the bandstand stairs has running slope of up to 6.9%. Recommendation: Replace sidewalk. (75 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Sidewalk to Bandstand Stairs | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 750
7 | 1C | Priority 1: Curb Ramps | The right-hand ramp and landing have a cross slope ranging from 2.6% to 3.4%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C2 | Southeast Curb Ramp | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 6000
8 | 1A | Priority 1: Accessible Routes | The sidewalk around the bandstand has cross slopes ranging from 2.5% to 5.8% and openings greater than 1/2". Recommendation: Remove and replace sidewalk. (480 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Bandstand Perimeter Sidewalk | kgoss@abyd.com | 0 | 17 | red | No | 0 | 0 | Yes | 4800
9 | 4D | Priority 4: Drinking Fountains | The single drinking fountain is accessible, but no standing height fountain is provided. Recommendation: Install a second fountain with the spout 38" to 43" high. | May 10, 2021 @ 19:00 | open | Issue | C2 | Drinking Fountain | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 3750
10 | 1A | Priority 1: Accessible Routes | The sidewalk to and around the fountain has a cross slope ranging from 2.7% to 8%. Recommendation: Remove and replace sidewalk. (600 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Fountain Perimeter Sidewalk | kgoss@abyd.com | 0 | 16 | red | No | 0 | 0 | Yes | 6000
11 | 1A | Priority 1: Accessible Routes | The route from the perimeter sidewalk to the back of the bandstand has multiple changes in level greater than 1/2". Recommendation: Replace sidewalk. (75 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Sidewalk to Rear Bandstand | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 750
12 | 1A | Priority 1: Accessible Routes | The south sidewalk has an abrupt change in level of 1/2" at the perimeter sidewalk. Recommendation: Grind edge to a 1:2 slope. | May 10, 2021 @ 19:00 | open | Issue | C3 | South Sidewalk to Memorial | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 200
13 | 1A | Priority 1: Accessible Routes | The sidewalk from the north perimeter sidewalk has a running slope of up to 8.3% and changes in level in excess of 1/2". Recommendation: Remove and replace sidewalk. (75 SF) | May 10, 2021 @ 19:00 | open | Issue | C3 | North Sidewalk to Memorial | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 750
14 | 1A | Priority 1: Accessible Routes | The sidewalk around the memorial has cross slopes ranging from 2.5% to 3.5% and excessive gaps and changes in level. Recommendation: Remove and replace sidewalk. (660 SF) | May 10, 2021 @ 19:00 | open | Issue | C3 | Memorial Perimeter Sidewalk | kgoss@abyd.com | 0 | 23 | red | No | 0 | 0 | Yes | 6600
15 | 2P | Priority 2: Protruding Objects | The north side of the sidewalk around the memorial has low tree branches with an overhead clearance of only 70". Recommendation: Trim tree branches. | May 10, 2021 @ 19:00 | open | Issue | C3 | Memorial Perimeter Sidewalk | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 500
16 | 2A | Priority 2: Accessible Routes | The north corner of the sidewalk has a cross slope of approximately 2.4% Recommendation: Remove and replace sidewalk. (100 SF) | May 10, 2021 @ 19:00 | open | Issue | C3 | Memorial Interior Sidewalk | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 1000
17 | 2P | Priority 2: Protruding Objects | The route from the perimeter sidewalk to the back of the bandstand has low tree branches with an overhead clearance of only 74". Recommendation: Trim tree branches. | May 10, 2021 @ 19:00 | open | Issue | C2 | Sidewalk to Rear Bandstand | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 500
18 | 1A | Priority 1: Accessible Routes | The two connecting decomposed granite paths are not stable or firm and have excessive changes in level. Recommendation: Replace route with paved sidewalk. (40 SF) | Jun 24, 2021 @ 13:54 | open | Issue | C2 | Fountain Perimeter Sidewalk | kgoss@abyd.com | 0 | 8 | red | No | 0 | 0 | Yes | 1000
1 | 1P | Priority 1: Parking | The three accessible spaces and access aisles facing the building have running slopes of 2.7% to 4.4%. Recommendation: Replace asphalt surface. | May 10, 2021 @ 19:00 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com | 0 | 8 | red | No | 0 | 0 | Yes | 10000
4 | 1P | Priority 1: Parking | The two accessible spaces and access aisle across the drive have a running slope of 2.6% to 3.8%. Recommendation: Replace asphalt surface. | May 10, 2021 @ 19:00 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 6500
6 | 1C | Priority 1: Curb Ramps | The landing and both runs of the parallel curb ramp have a cross slope ranging from 3.2% to 4%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com | 0 | 11 | red | No | 0 | 0 | Yes | 5000
7 | 1A | Priority 1: Accessible Routes | Sidewalk has a 1" gap between panels. Recommendation: Fill gap with caulking material. | May 10, 2021 @ 19:00 | open | Issue | C3 | Route from East Parking | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 100
9 | 1P | Priority 1: Parking | The northernmost accessible space has an uneven surface and a cross slope of approximately 2.8%. Recommendation: Replace asphalt paving and restripe. | May 10, 2021 @ 19:00 | open | Issue | C2 | West Parking Lot | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 3000
10 | 1C | Priority 1: Curb Ramps | The landing and both runs of the parallel curb ramp have a cross slope ranging from 3.1% to 4.9%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C2 | West Parking Lot | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 5000
11 | 1A | Priority 1: Accessible Routes | The sidewalk has a cross slope of to 4.6% and changes in level of up to 1-3/4" in two locations. Recommendation: Remove and replace length of sidewalk. (4panels, 132 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Route to Book Drop | kgoss@abyd.com | 0 | 10 | red | No | 0 | 0 | Yes | 1320
12 | 1A | Priority 1: Accessible Routes | The route connecting to the public sidewalk has a cross slope of approximately 2.5%. Recommendation: Remove and replace sidewalk. (25 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | May 10, 2021 @ 19:00 | open | Issue | C1 | West Route from Public ROW | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 250
13 | 1C | Priority 1: Curb Ramps | The curb ramp at the west driveway has a cross slope of approximately 4.8%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | West Route from Public ROW | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 2500
14 | 1C | Priority 1: Curb Ramps | The parallel curb ramp at the west end of the circle drive has running slopes of 9 and 9.7% on each side. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | West Route from Public ROW | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 5000
15 | 1A | Priority 1: Accessible Routes | The sidewalk has a cross slope of approximately 3.1%. Recommendation: Remove and replace sidewalk. (1 large panel, 120 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 1200
16 | 1A | Priority 1: Accessible Routes | The route connecting to the public sidewalk has a cross slope of approximately 7.5%. Recommendation: Remove and replace sidewalk. (25 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 250
17 | 1C | Priority 1: Curb Ramps | The curb ramp at the east driveway has a cross slope of approximately 2.7% and a 3/4" change in level at the bottom. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 2500
18 | 1C | Priority 1: Curb Ramps | The parallel curb ramp at the east end of the circle drive has excessive cross slopes on both runs and the landing and excessive running slopes on the right-hand run. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com | 0 | 10 | red | No | 0 | 0 | Yes | 5000
19 | 1A | Priority 1: Accessible Routes | The sidewalk around the tree has a cross slope of up to 3.1%. Recommendation: Remove and replace sidewalk. (2 panels, 96 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | Yes | 960
20 | 1Z | Priority 1: Loading Zones | The covered vehicular area at the Book Drop has a cross slope of approximately 5.7%. Recommendation: Remove and replace paving in this area to ensure a maximum slope of 2% in all directions. Stripe access aisle. (260 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Book Drop | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 3500
23 | 1A | Priority 1: Accessible Routes | A portion of sidewalk leading to the reading garden has a cross slope of approximately 3.1%. Recommendation: Remove and replace sidewalk. (One panel, 42 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Route to Reading Garden | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 420
24 | 4D | Priority 4: Drinking Fountains | One accessible drinking fountain is provided, but no standing height fountain is provided. Recommendation: Install a standing height fountain with the spout outlet 38" to 43" high. | May 10, 2021 @ 19:00 | open | Issue | A1 | Restroom Foyer | kgoss@abyd.com | 0 | 1 | red | No | 0 | 0 | Yes | 3750
25 | 3M | Priority 3: Mirrors | The mirror is mounted with the bottom of the reflective surface 48-1/2" high. Recommendation: Install a mirror with the bottom of the reflective surface 40" high maximum. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 300
26 | 3B | Priority 3: Baby Changing Stations | The baby changing table has a rim height of 37”. Recommendation: Modify the table to have a maximum height of 34". | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 3500
27 | 3P | Priority 3: Protruding Objects | The hand dryer protrudes 6-1/2" at 39" high. Recommendation: Relocate hand dryer. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 500
28 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible stall has only 6” of clearance past the latch on the pull side. And no door pull is installed on the inside of the stall door. Recommendation: Swing door inward. Install door pull. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 450
29 | 3W | Priority 3: Water Closets | The centerline of the water closet is 18-1/2" from the side wall. Recommendation: Reposition water closet with the centerline 16" to 18" from the wall. (Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 2500
30 | 3G | Priority 3: Grab Bars | The grab bars are installed with the top of the gripping surface 36-3/4" high, and the side grab bar has only 6" of clearance above the bar. Recommendation: Reposition grab bar with the top of the gripping surface 33" to 36" high. Relocate toilet paper dispenser below grab bar. (Note: If these elements were installed prior to March 15, 2012, this condition may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 600
31 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible stall has only 6” of clearance past the latch on the pull side. No door pull is installed on the inside of the stall door, and the door is not self-closing. Recommendation: Swing door inward. Install door pull. Adjust hinges. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 450
32 | 3G | Priority 3: Grab Bars | The grab bars are installed with the top of the gripping surface 36-1/2" high, and the side grab bar has only 6" of clearance above the bar. Recommendation: Reposition grab bar with the top of the gripping surface 33" to 36" high. Relocate toilet paper dispenser below grab bar. (Note: If these elements were installed prior to March 15, 2012, this condition may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 600
33 | 3M | Priority 3: Mirrors | The mirror is mounted with the bottom of the reflective surface 48-3/4" high. Recommendation: Install a mirror with the bottom of the reflective surface 40" high maximum. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 300
34 | 3P | Priority 3: Protruding Objects | The hand dryer protrudes 6-1/2" at 39" high. Recommendation: Relocate hand dryer. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 500
35 | 3B | Priority 3: Baby Changing Stations | The baby changing table requires a reach of 52-1/2" to open and is located within the required maneuvering area of the door. (Please note that TDLR considers baby changing stations to be protruding objects in their open position where the bottom of the table is more than 27" high. In this instance, the table obstructs the door maneuvering clearance in the open position.) Recommendation: Relocate baby changing station outside of the door maneuvering area and position with the handle no higher than 48". | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 450
36 | 2B | Priority 2: Tables | The computer tables are 24-3/4" high and have a knee space height of 23-1/4". Recommendation: Install at least one computer station with a counter height of 26-30" and a knee space height of 24" minimum for children's use. | May 10, 2021 @ 19:00 | open | Issue | A1 | Children's Library | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 450
37 | 4V | Priority 4: Vending Machines | The vending machines have card swipes positioned 59" and 65" high. Recommendation: Replace vending machines. | May 10, 2021 @ 19:00 | open | Issue | A1 | Vending | kgoss@abyd.com | 0 | 6 | red | No | 0 | 0 | 0 | Unspecified
38 | 2H | Priority 2: Reach Range | The coffee bar counter is 36” high. Recommendation: Lower the counter to 34" high maximum to allow reach to self-serve elements. | May 10, 2021 @ 19:00 | open | Issue | A1 | Coffee Bar | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 3500
39 | 2B | Priority 2: Tables | The round tables throughout the stacks area do not have accessible toe space depth below. Recommendation: Install at least one accessible table. | May 10, 2021 @ 19:00 | open | Issue | A1 | Stacks | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 450
40 | 2B | Priority 2: Tables | Booth tables do not have adequate toe clearance for a forward approach. Recommendation: Install at least one accessible booth table. | May 10, 2021 @ 19:00 | open | Issue | A1 | Teen Area | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 450
41 | 2C | Priority 2: Counters | The charging station counter is 43" high. Recommendation: Modify a portion of the counter to a maximum height of 34". | May 10, 2021 @ 19:00 | open | Issue | A1 | Stacks | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 7500
43 | 2C | Priority 2: Counters | The catalog computers are located on a 41-1/2" high counter with no knee and toe space. Recommendation: Relocate at least one computer to an accessible table. | May 10, 2021 @ 19:00 | open | Issue | A1 | Catalog Computers | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 450
44 | 2C | Priority 2: Counters | The self-serve library card sign-up station has a counter height of 38-1/2". Recommendation: Lower the counter to 34" high maximum with compliant knee and toe space below. | May 10, 2021 @ 19:00 | open | Issue | A1 | Library Card Sign Up | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 450
45 | 1A | Priority 1: Accessible Routes | The accessible route from the public sidewalk across the east drive way has a cross slope of approximately 3.3%. Recommendation: Replace asphalt along this route. (100 SF) | Jun 25, 2021 @ 09:49 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 1000
46 | 1A | Priority 1: Accessible Routes | A portion of sidewalk leading to the reading garden has a 1/2" abrupt change in level. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 10:07 | open | Issue | C1 | Route to Reading Garden | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 200
47 | 1A | Priority 1: Accessible Routes | The sidewalk has a 1/2" abrupt change in level between panels. Recommendation: Grind edge to a maximum 1:2 slope. | Jun 25, 2021 @ 10:15 | open | Issue | C1 | Route to Reading Garden | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 200
51 | 2A | Priority 2: Accessible Routes | Sidewalk has a cross slope of up to 2.6%. Recommendation: Remove and replace sidewalk. (1 panel, 72 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 10:34 | open | Issue | C1 | Reading Garden | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 720
52 | 2A | Priority 2: Accessible Routes | Sidewalk has a cross slope of up to 2.6%. Recommendation: Remove and replace sidewalk. (1 panel, 72 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 10:36 | open | Issue | C1 | Reading Garden | kgoss@abyd.com | 0 | 2 | red | No | 0 | 0 | Yes | 720
53 | 2A | Priority 2: Accessible Routes | Sidewalk has a 1/2" abrupt change in level between panels. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 10:37 | open | Issue | C1 | Reading Garden | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 200
54 | 2A | Priority 2: Accessible Routes | Sidewalk has a cross slope of up to 2.7%. Recommendation: Remove and replace sidewalk. (3 panels, 168 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 10:39 | open | Issue | C1 | Reading Garden | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 1680
55 | 2A | Priority 2: Accessible Routes | Sidewalk has three locations with an approximate 1" gap between panels. Recommendation: Fill gaps with caulking material. | Jun 25, 2021 @ 10:40 | open | Issue | C1 | Reading Garden | kgoss@abyd.com | 0 | 5 | red | No | 0 | 0 | Yes | 300
56 | 1P | Priority 1: Parking | Of the 9 accessible parking spaces provided, only one is designated as a van space. Recommendation: Add a van designation sign to at least one more space in either the east or west lot with an overall width of 16' (8'/8' or 11'/5'). | Jun 25, 2021 @ 10:44 | open | Issue | C3 | Parking - General | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 100
57 | 1A | Priority 1: Accessible Routes | Route has an approximate 1/2" abrupt change in level at joint. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 10:53 | open | Issue | C3 | Route from East Parking | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 200
58 | 1A | Priority 1: Accessible Routes | Route has an approximate 1/2" abrupt change in level at joint. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 11:00 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 200
59 | 1A | Priority 1: Accessible Routes | Sidewalk has a 1" gap between panels. Recommendation: Fill gap with caulking material. | Jun 25, 2021 @ 11:03 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 100
60 | 1A | Priority 1: Accessible Routes | The covered approach to the main entrance has a cross slope of up to 2.7%. Recommendation: Remove and replace sidewalk. (2 large panels, 160 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 11:11 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com | 0 | 4 | red | No | 0 | 0 | Yes | 1600
61 | 1P | Priority 1: Parking | The vertical sign at the southernmost accessible parking space is mounted with the bottom of the sign less than 60" high. Recommendation: Reposition sign. | Jun 25, 2021 @ 11:16 | open | Issue | C2 | West Parking Lot | kgoss@abyd.com | 0 | 3 | red | No | 0 | 0 | Yes | 100
62 | 1P | Priority 1: Parking | The vertical parking signs at the three spaces facing the building are mounted less than 60" to the bottom. Recommendation: Reposition signs with the bottom at least 60" high. | Jun 25, 2021 @ 11:31 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com | 0 | 7 | red | No | 0 | 0 | Yes | 300
1 | 2A | Priority 2: Accessible Routes | No accessible route is provided to the stage or vending machines. Recommendation: Install a platform lift for access to the stage. | May 10, 2021 @ 19:00 | open | Issue | A1 | Stage | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 10000
2 | 4V | Priority 4: Vending Machines | The card slide at the vending machine is 54” high. Recommendation: Replace vending machine. | May 10, 2021 @ 19:00 | open | Issue | A1 | Stage | 0 | 0 | 4 | red | No | 0 | 0 | 0 | Unspecified
3 | 2P | Priority 2: Protruding Objects | The bleeding control kit projects 10" at 45" high. Recommendation: Relocate or add cane barrier below. | May 10, 2021 @ 19:00 | open | Issue | A1 | Lunchroom Corridor | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 500
4 | 2D | Priority 2: Doors | Door has only 16” of clearance past the latch on the pull side. Recommendation: Modify door configuration to provide a minimum 18" clearance past the latch. | May 10, 2021 @ 19:00 | open | Issue | A1 | Lunchroom/Classroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 2750
5 | 2P | Priority 2: Protruding Objects | Drinking fountains project approximately 7" from the base at 28-1/2" and 32" high. Recommendation: Lower accessible fountain so the bottom of the apron is exactly 27", and install an apron to the high fountain. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator Lobby | 0 | 0 | 7 | red | No | 0 | 0 | Yes | 3700
6 | 2P | Priority 2: Protruding Objects | The defibrillator box projects 7-1/2" at 48" high. Recommendation: Relocate box or install a partially recessed model. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator Lobby | 0 | 0 | 5 | red | No | 0 | 0 | Yes | 500
7 | 2C | Priority 2: Counters | The kitchen serving counter is 35” high. Recommendation: Modify at least a portion of counter to a maximum 34" height. | May 10, 2021 @ 19:00 | open | Issue | A1 | Lunchroom Corridor | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 3500
8 | 3D | Priority 3: Doors | Restroom entry door has only 51” of side approach clearance. Recommendation: Modify toilet partitions to provide a full 54". | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 1250
9 | 3L | Priority 3: Lavatories | The lavatory has a rim height of 35" and no knee space below. Recommendation: Reconfigure lavatory with rim 34" high maximum and knee and toe space for a forward approach. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 6 | red | No | 0 | 0 | Yes | 1750
10 | 3P | Priority 3: Protruding Objects | The paper towel dispenser projects 9" at a 47" high. Recommendation: Relocate dispenser. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 500
11 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is mounted 53" high. Recommendation: Install hook at a maximum height of 48". (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 50
12 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing and does not have a pull on the inside. Recommendation: Adjust door hinges. Install door pull. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 325
13 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is centered 4" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 225
14 | 3G | Priority 3: Grab Bars | The rear grab bar in the wheelchair accessible toilet stall has only 1" of clearance below the bar. Recommendation: Reposition bar to 1-1/2" above toilet tank. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 200
15 | 3B | Priority 3: Baby Changing Stations | The baby changing station requires a side reach height of 51" to open and has a surface slope of approximately 7.5% within the clear floor space. Recommendation: Replace baby changing station and locate it where the floor is level and outside of circulation paths. TDLR requires baby changing stations to be considered in their open position when considering protruding objects. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 9 | red | No | 0 | 0 | Yes | 1000
16 | 3H | Priority 3: Showers | The accessible shower is not equipped with a handheld shower wand (missing), and the knob adjustment requires tight grasping and twisting of the wrist. Recommendation: Install a compliant handheld shower assembly. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 600
17 | 3D | Priority 3: Doors | Restroom entry door has only 53” of side approach clearance. Recommendation: Modify toilet partition to provide a full 54". Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 1250
18 | 3P | Priority 3: Protruding Objects | The paper towel dispenser projects 9" at a 47" high. Recommendation: Relocate dispenser. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 500
19 | 3L | Priority 3: Lavatories | The lavatory has a rim height of 35" and no knee space below. Recommendation: Reconfigure lavatory with rim 34" high maximum and knee and toe space for a forward approach. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 1750
20 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is mounted 53" high. Recommendation: Install hook at a maximum height of 48". (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 50
21 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing and does not have a pull on the inside. Recommendation: Adjust door hinges. Install door pull. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 325
22 | 3G | Priority 3: Grab Bars | The rear grab bar in the wheelchair accessible toilet stall has only 1" of clearance below the bar. Recommendation: Reposition bar to 1-1/2" above toilet tank. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 200
23 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is centered 4" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 225
24 | 3H | Priority 3: Showers | The accessible shower is not equipped with a handheld shower wand (missing), and the knob adjustment requires tight grasping and twisting of the wrist. Recommendation: Install a compliant handheld shower assembly. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 600
25 | 2D | Priority 2: Doors | Two sets of double doors have vision panels positioned with the bottom of the glass 44" high. Recommendation: Replace doors with ones have vision panels positioned with the bottom no more than 43". (Note: If the doors were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Gymnasium | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 3000
26 | 2P | Priority 2: Protruding Objects | Alarm panel box projects 5" from the wall at 52" high. Recommendation: Provide cane barrier below. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator Lobby | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 500
27 | 2E | Priority 2: Elevators | The emergency alarm button is centered 31" high. Recommendation: Relocate panel with alarm button 35" high minimum. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 1000
28 | 2D | Priority 2: Doors | Vision panels in 4 doors have the bottom of the glass positioned 45-1/2" high. Recommendation: Replace doors with ones have vision panels positioned with the bottom no more than 43". (Note: If the doors were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Corridor | 0 | 0 | 6 | red | No | 0 | 0 | Yes | 3000
29 | 2P | Priority 2: Protruding Objects | The high drinking fountain projects approximately 7" from the base at 33" high. Recommendation: Install an apron to the high fountain to bring the bottom to no more than 27" high. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Corridor | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 300
30 | 3D | Priority 3: Doors | The door has a side approach width of only 40-1/2". Recommendation: Install automatic door opener. Alternatively, replace lavatory with a more shallow fixture, swing door outward and remove closer. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 4000
31 | 3R | Priority 3: Reach Range | Coat hook is mounted 68" high. Recommendation: Install a coat hook no higher than 48". | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 50
32 | 3L | Priority 3: Lavatories | Lavatory drainpipes do not have insulation. Recommendation: Install pipe insulation kit. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom | 0 | 0 | 1 | red | No | 0 | 0 | Yes | 200
33 | 3W | Priority 3: Water Closets | Water closet is centered 18-1/2" from side wall and seat height is only 16". Recommendation: Replace water closet and install with centerline 16" to 18" from wall. Ensure seat height of 17" to 19". (Note: If this element was installed prior to March 15, 2012, the centerline dimension may enjoy safe harbor until replaced. Add a thicker seat to achieve a height of 17" to 19".) | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom | 0 | 0 | 5 | red | No | 0 | 0 | Yes | 2625
34 | 3G | Priority 3: Grab Bars | The side grab bar is only 36" long and extends only 48" from the rear wall. Recommendation: Replace with a minimum 42" long grab bar extending 54" from the back wall. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 285
35 | 2H | Priority 2: Reach Range | Coat hooks are positioned 66" high. Recommendation: Install at least one hook no higher than 48". | May 10, 2021 @ 19:00 | open | Issue | A1 | Library | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 50
36 | 1P | Priority 1: Parking | All 4 accessible parking spaces and access aisles have running slopes ranging from 4.3% to 5.9% and a crack in the asphalt. Recommendation: Remove and replace asphalt in this area. | May 11, 2021 @ 19:00 | open | Issue | C2 | Parking Lot | 0 | 0 | 12 | red | No | 0 | 0 | Yes | 13500
37 | 1A | Priority 1: Accessible Routes | Sidewalk has a cross slope of approximately 2.6%. Recommendation: Remove and replace sidewalk. (1 panel, 30 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | May 11, 2021 @ 19:00 | open | Issue | C2 | Route from Public ROW | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 300
38 | 1A | Priority 1: Accessible Routes | A portion of the sidewalk has a cross slope of up to 2.7%, excessive gaps and excessive change in level. Recommendation: Remove and replace sidewalk. (2 panels, 50 SF) | May 11, 2021 @ 19:00 | open | Issue | C2 | Route from Accessible Parking | 0 | 0 | 11 | red | No | 0 | 0 | Yes | 500
39 | 1A | Priority 1: Accessible Routes | The route has an approximate 1" gap on each side of the metal coverplate. Recommendation: Add caulking material. | Jun 28, 2021 @ 10:22 | open | Issue | C2 | Route from Public ROW | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 200
40 | 1A | Priority 1: Accessible Routes | Sidewalk has approximate 1" wide openings between panels in two locations. Recommendation: Add caulking material. | Jun 28, 2021 @ 10:23 | open | Issue | C2 | Route from Public ROW | 0 | 0 | 7 | red | No | 0 | 0 | Yes | 200
41 | 1A | Priority 1: Accessible Routes | Sidewalk has approximate 1" wide openings between panels in two locations. Recommendation: Add caulking material. | Jun 28, 2021 @ 10:54 | open | Issue | C2 | Route from Accessible Parking | 0 | 0 | 7 | red | No | 0 | 0 | Yes | 200
42 | 3W | Priority 3: Water Closets | The toilet paper dispenser is centered 4" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 13:53 | open | Issue | A1 | Upstairs Women's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 225
43 | 3W | Priority 3: Water Closets | The paper towel dispenser overlaps the 60" wide clear floor space at the water closet. Recommendation: Relocate paper towel dispenser outside of required water closet clearance. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 13:53 | open | Issue | A1 | Upstairs Women's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 200
44 | 3D | Priority 3: Doors | The door has a side approach width of only 39-1/2". Recommendation: Install automatic door opener. Alternatively, replace lavatory with a more shallow fixture, swing door outward and remove closer. | Jun 28, 2021 @ 14:04 | open | Issue | A1 | Upstairs Men's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 4000
45 | 3R | Priority 3: Reach Range | Coat hook is mounted 68" high. Recommendation: Install a coat hook no higher than 48". | Jun 28, 2021 @ 14:07 | open | Issue | A1 | Upstairs Men's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 50
46 | 3L | Priority 3: Lavatories | Lavatory drainpipes do not have insulation. Recommendation: Install pipe insulation kit. | Jun 28, 2021 @ 14:08 | open | Issue | A1 | Upstairs Men's Restroom | 0 | 0 | 1 | red | No | 0 | 0 | Yes | 200
47 | 3W | Priority 3: Water Closets | Water closet has a seat height of only 16", and the flush is mounted on the wall side of the fixture. Recommendation: Replace water closet. | Jun 28, 2021 @ 14:09 | open | Issue | A1 | Upstairs Men's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 1000
48 | 3W | Priority 3: Water Closets | The paper towel dispenser overlaps the 60" wide clear floor space at the water closet. Recommendation: Relocate paper towel dispenser outside of required water closet clearance. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 14:18 | open | Issue | A1 | Upstairs Men's Restroom | 0 | 0 | 3 | red | No | 0 | 0 | Yes | 200
50 | 3G | Priority 3: Grab Bars | The side grab bar is only 36" long and extends only 48" from the rear wall. Recommendation: Replace with a minimum 42" long grab bar extending 54" from the back wall. | Jun 28, 2021 @ 14:20 | open | Issue | A1 | Upstairs Men's Restroom | 0 | 0 | 4 | red | No | 0 | 0 | Yes | 285
51 | 3W | Priority 3: Water Closets | The toilet paper dispenser is centered approximately 5" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 14:21 | open | Issue | A1 | Upstairs Men's Restroom | 0 | 0 | 2 | red | No | 0 | 0 | Yes | 225
TOTAL | [16 empty] | 363785

## Civic_Convention_Center
Task # | Stamp | Title | Description | Date | Status | Type | Sheet | Location | Created By | Assigned To | # Photos | Color | Archived | Start Date | Due Date | Cost Impact | Cost Impact Amount | Schedule Impact | Schedule Impact Amount (days) | List | Last Updated | Closed On
1 | 1P | Priority 1: Parking | The van accessible parking space and access aisle have a running slope of up to 3.3% and has some cracking and gaps in the asphalt. Recommendation: Replace asphalt surface at parking space and access aisle. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 3500 |  |  |  | Oct 14, 2019 @ 16:34
3 | 1P | Priority 1: Parking | The three easternmost accessible parking spaces have cracking and gaps in the asphalt, and the easternmost accessible parking space has a running slope of up to 2.8%. Recommendation: Replace asphalt surface at parking spaces and access aisles. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 7000 |  |  |  | Oct 14, 2019 @ 16:38
4 | 1A | Priority 1: Accessible Routes | The route from the van accessible parking space to the public sidewalk has an approximate 1" wide gap. Recommendation: Fill gap with caulking material. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 250 |  |  |  | Oct 14, 2019 @ 17:03
5 | 1A | Priority 1: Accessible Routes | The route from the easternmost accessible parking spaces to the public sidewalk has two approximately 1" wide gaps. Recommendation: Fill gaps with caulking material. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:39
6 | 1A | Priority 1: Accessible Routes | The route from the two center accessible parking spaces to the public sidewalk has two approximately 1" wide gaps. Recommendation: Fill gaps with caulking material. | May 11, 2021 @ 19:00 | open | Issue | C3 | Public Lot off S Castell | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:38
7 | 1R | Priority 1: Ramps | The ramp at the south entrance has the following issues: 1) Excessive gaps surrounding the bottom landing 2) Missing handrail extension on one side of the top and bottom landings 3) Intermediate landing is less than 60" x 60" clear 4) Upper landing has a cross slope of approximately 2.8% Recommendation: Remove and replace ramp. | May 11, 2021 @ 19:00 | open | Issue | C3 | Route to South Entrance | kgoss@abyd.com |  | 12 | red | No |  |  | Yes | 7500 |  |  |  | Oct 14, 2019 @ 16:34
8 | 1E | Priority 1: Entrances | The door maneuvering area on the pull side of the entrance doors has a running slope of approximately 3.1%. Recommendation: Replace landing area at door and stair. | May 11, 2021 @ 19:00 | open | Issue | C3 | South Entrance | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 12500 |  |  |  | Oct 14, 2019 @ 16:38
9 | 1P | Priority 1: Parking | Both accessible parking spaces and the shared access aisle have excessive cross slopes ranging from 3.3% to 3.9%. Recommendation: Replace asphalt surface at parking spaces. | May 11, 2021 @ 19:00 | open | Issue | C2 | North Parking Lot | kgoss@abyd.com |  | 9 | red | No |  |  | Yes | 6500 |  |  |  | Oct 14, 2019 @ 16:36
10 | 1A | Priority 1: Accessible Routes | The base of the curb ramp has a change in level of approximately 1/2". Recommendation: Grind the edge to create a maximum 1:2 bevel. | May 11, 2021 @ 19:00 | open | Issue | C2 | Route from South Accessible Parking | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:38
12 | 2H | Priority 2: Reach Range | The shelf above the clothes rod is 51-1/2" high. Recommendation: Lower a portion of rod and shelf to a maximum height of 48". (Note: If this shelf was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 11, 2021 @ 19:00 | open | Issue | A1 | Women's Dressing Room | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:37
14 | 2P | Priority 2: Protruding Objects | A series of panels and equipment boxes project more than 4" from the wall between 27" and 80" high. Recommendation: Add cane detection railing below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Backstage Vestibule | kgoss@abyd.com |  | 8 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:34
15 | 2P | Priority 2: Protruding Objects | The panel box near the ballroom projects more than 4" from the wall between 27" and 80" high. Recommendation: Add cane detection railing below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Loading Dock Corridor | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:41
16 | 2R | Priority 2: Ramps | The ramp to the stage has the following noncompliant conditions: 1) The slope of both runs are approximately 8.5%; however, it may be considered within reasonable construction tolerance 2) The bottom landing has an approximate 1/2" high change in level 3) The intermediate landing is not 60" x 60" clear Recommendation: Remove and replace ramp. | May 11, 2021 @ 19:00 | open | Issue | A1 | Ballroom | kgoss@abyd.com |  | 10 | red | No |  |  | Yes | 7500 |  |  |  | Oct 14, 2019 @ 16:36
17 | 2D | Priority 2: Doors | Door vision panels in 12 doors (Exhibit Hall and Kitchen) are positioned with the bottom of the glass 56-1/4" high. Recommendation: Install doors with vision panels no higher than 43". (Note: If these doors were installed prior to March 15, 2012, they may enjoy safe harbor until they are replaced.) | May 11, 2021 @ 19:00 | open | Issue | A1 | Loading Dock Corridor | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 3000 |  |  |  | Oct 14, 2019 @ 16:36
18 | 2D | Priority 2: Doors | Door vision panels in the 5 conference room doors are positioned with the bottom of the glass more than 43" high. Recommendation: Install doors with vision panels no higher than 43". (Note: If these doors were installed prior to March 15, 2012, they may enjoy safe harbor until they are replaced.) | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 3750 |  |  |  | Oct 14, 2019 @ 16:35
19 | 3D | Priority 3: Doors | The entrance door requires more than 5 lbs of force to open. Recommendation: Adjust door closer. | May 11, 2021 @ 19:00 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 150
20 | 3D | Priority 3: Doors | The entrance door requires more than 5 lbs of force to open. Recommendation: Adjust door closer. | May 11, 2021 @ 19:00 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 150
21 | 2P | Priority 2: Protruding Objects | The Blood Control Kit and AED boxes project more than 4" from the wall at a height of 27" to 80" high. Recommendation: Add cane detection element below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com |  | 8 | red | No |  |  |  | 500 |  |  |  | Oct 14, 2019 @ 16:40
22 | 2P | Priority 2: Protruding Objects | The wall-mounted TV outside of the office entrance projects more than 4" from the wall at a height of 27" to 80". Recommendation: Add cane detection element below. | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:35
23 | 4V | Priority 4: Vending Machines | The two vending machines have card slides that are 50" and 58" high. Recommendation: Replace vending machines with compliant models. | May 11, 2021 @ 19:00 | open | Issue | A1 | Concourse | kgoss@abyd.com |  | 5 | red | No |  |  |  | Unspecified
25 | 2K | Priority 2: Sinks | The sinks in each of the 5 conference rooms have a toe space that is only 7" high. Recommendation: Modify panel to provide a minimum 9" high toe space. | May 13, 2021 @ 14:50 | open | Issue | A1 | Conference Rooms | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 8750 |  |  |  | Oct 14, 2019 @ 16:35
26 | 2D | Priority 2: Doors | Four doors (ballroom and kitchen) do not have a smooth surface on the bottom 10" of the push side due to installed door stops. Recommendation: Remove door stops. (Note: If these doors were installed prior to March 15, 2012, they may enjoy safe harbor until they are replaced.) | May 13, 2021 @ 15:03 | open | Issue | A1 | Loading Dock Corridor | kgoss@abyd.com |  | 3 | red | No |  |  |  | Unspecified |  |  |  | Oct 14, 2019 @ 16:37
27 | 2E | Priority 2: Elevators/Lifts | The platform lift to the stage has a clear width of only 34-1/2". Recommendation: Install a compliant platform lift with a minimum clear width of 36". (Note: If this lift was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:29 | open | Issue | A1 | Exhibit Hall | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 12000 |  |  |  | Oct 14, 2019 @ 16:42
28 | 3R | Priority 3: Reach Range | The openings of both paper towel dispensers are 50" and 49 1/2" high. Recommendation: Reposition at least one dispenser with opening no higher than 48". (Note: If the dispensers were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:32 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 200
29 | 3B | Priority 3: Baby Changing Stations | The surface of the baby changing table is 34-1/2" high in the open position. (Please note that TDLR considers baby changing stations to be protruding objects in their open position where the bottom of the table is more than 27" high. In this instance, the table obstructs the door maneuvering clearance in the open position.) Recommendation: Relocate baby changing station outside of the door maneuvering area and position with the top of the table 28" to 34" high in the open position. | May 14, 2021 @ 09:34 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:36
30 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is 54" high. Recommendation: Install a hook positioned no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:37 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 50
31 | 3G | Priority 3: Grab Bars | The grab bars in the wheelchair accessible toilet stall are positioned with the top of the bar 36-1/2" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. See related Item #32. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 09:39 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:41
32 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is not centered 7 to 9" in front of the water closet. Recommendation: Reposition the dispenser below the grab bar with the centerline 7" to 9" in front of the water closet. See related Item #31. (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:41 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 225
33 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:42 | open | Issue | A1 | South Women's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 100 |  |  |  | Oct 14, 2019 @ 17:01
34 | 3W | Priority 3: Water Closets | The water closet in the wheelchair accessible toilet stall is centered approximately 18 1/2" from the side partition. Recommendation: Reposition the water closet with the centerline 16" to 18" from side wall. (Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:45 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 2500
35 | 3B | Priority 3: Baby Changing Stations | The surface of the baby changing table is 35" high in the open position. (Please note that TDLR considers baby changing stations to be protruding objects in their open position where the bottom of the table is more than 27" high.) Recommendation: Reposition the baby changing station so that the top of the table 28" to 34" high and the bottom of the table is exactly 27" in the open position. | May 14, 2021 @ 09:47 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:40
36 | 3R | Priority 3: Reach Range | The openings of both paper towel dispensers are 50" high. Recommendation: Reposition dispenser with opening no higher than 48". (Note: If the dispensers were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:47 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 200
37 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing. Recommendation: Adjust door hinges. | May 14, 2021 @ 09:48 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 225 |  |  |  | Oct 14, 2019 @ 16:42
38 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:50 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 100 |  |  |  | Oct 14, 2019 @ 16:39
39 | 3G | Priority 3: Grab Bars | The grab bars in the wheelchair accessible toilet stall are positioned with the top of the bar 37" high. Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. (Note: If the grab bars were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 09:50 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:42
40 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is 54" high. Recommendation: Install a hook positioned no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 09:51 | open | Issue | A1 | South Men's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 50
41 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is 54" high. Recommendation: Install a coat hook no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:01 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 50
42 | 3R | Priority 3: Reach Range | The coat hook in the ambulatory accessible toilet stall is 54" high. Recommendation: Install a coat hook no higher than 48". (Note: If the hook was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:01 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 50
43 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:03 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 100 |  |  |  | Oct 14, 2019 @ 16:41
44 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:03 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 100
45 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing. Recommendation: Adjust door hinge. | May 14, 2021 @ 10:04 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 225
46 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall is not self-closing. Recommendation: Adjust door hinges. | May 14, 2021 @ 10:05 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 225
47 | 3G | Priority 3: Grab Bars | The grab bars in the wheelchair accessible toilet stall are positioned with the top of the bar 36-3/4" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser. Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. See related Item #48. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 10:07 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:39
48 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is not centered 7 to 9" in front of the water closet. Recommendation: Reposition the dispenser below the grab bar with the centerline 7" to 9" in front of the water closet. See related Item #47. (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:08 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 225
49 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the ambulatory accessible toilet stall is not centered 7 to 9" in front of the water closet. Recommendation: Reposition the dispenser below the grab bar with the centerline 7" to 9" in front of the water closet. See related Item #51. (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 10:08 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 225
50 | 3C | Priority 3: Toilet Compartments | The side approach width to the ambulatory accessible toilet stall is only 41" wide. A minimum 42" width is required. Recommendation: Reconfigure partitions to provide a minimum 42" clearance. | May 14, 2021 @ 10:09 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 2500
51 | 3G | Priority 3: Grab Bars | The grab bars in the ambulatory accessible toilet stall are positioned 13" from the rear wall and with the top of the bar 36-3/4" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser. Recommendation: Reposition grab bars 12" from the rear wall and 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. See related Item #49. | May 14, 2021 @ 10:11 | open | Issue | A1 | North Women's Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:41
52 | 3U | Priority 3: Urinals | The accessible urinal is positioned with the rim 18-1/4" high. Recommendation: Reposition urinal with the rim no higher than 17". | May 14, 2021 @ 10:13 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 1250
53 | 3M | Priority 3: Mirrors | The mirrors over each of the lavatories are positioned with the bottom of the reflective surface 40-3/4" high. Recommendation: Reposition one mirror with the bottom of the glass no higher than 40". | May 14, 2021 @ 11:19 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 300
54 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:21 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 100
55 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall does not have a pull on the inside. Recommendation: Install door pull. (Note: If the stall door and hardware were installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:22 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 100
56 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing. Recommendation: Adjust door hinges. | May 14, 2021 @ 11:23 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 225
57 | 3C | Priority 3: Toilet Compartments | The door to the ambulatory accessible toilet stall is not self-closing. Recommendation: Adjusts door hinges. | May 14, 2021 @ 11:24 | open | Issue | A1 | North Men's Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 225
58 | 2K | Priority 2: Sinks | The sink has a knee space height of only 25" below the sink. Recommendation: Replace sink with a shallower model. | May 14, 2021 @ 11:25 | open | Issue | A1 | Conference Kitchen | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 1000 |  |  |  | Oct 14, 2019 @ 16:40
59 | 2H | Priority 2: Reach Range | The soap dispenser is positioned with the operable part 51-3/4" high. Recommendation: Reposition dispenser with operable parts no more than 44" high. | May 14, 2021 @ 11:28 | open | Issue | A1 | Conference Kitchen | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:37
60 | 2H | Priority 2: Reach Range | The disposal switch and convenience outlets are positioned 47-3/4" high. Recommendation: Reposition the disposal switch and outlets with all operable parts and receptacles 46" high maximum. | May 14, 2021 @ 11:30 | open | Issue | A1 | Conference Kitchen | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 1000 |  |  |  | Oct 14, 2019 @ 16:35
61 | 2D | Priority 2: Doors | The door has only 17-1/2" of clearance past the strike on the pull side. Recommendation: Although the clearance is technically less than the allowable, this appears to be within reasonable tolerance. If this door is modified or replaced in the future, correction will be required. | May 14, 2021 @ 11:34 | open | Issue | A1 | Women's Dressing Room | kgoss@abyd.com |  | 3 | red | No |  |  |  | Unspecified |  |  |  | Oct 14, 2019 @ 16:33
62 | 3W | Priority 3: Water Closets | The water closet is centered approximately 18-1/4" from the side wall. Recommendation: Reposition the water closet with the centerline 16" to 18" from side wall.(Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:36 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 2500
63 | 3G | Priority 3: Grab Bars | The grab bars at the water closet are positioned with the top of the bar 36-1/2" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser Recommendation: Position grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:38 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:39
64 | 3W | Priority 3: Water Closets | The water closet has 48-1/2" of clear floor space width measured from the side wall to the edge of the lavatory. Recommendation: Enlarge restroom to allow a full 60" wide clearance at the water closet measured from side wall to edge of lavatory. (Note: If the water closet and lavatory were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:40 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 15000
65 | 3R | Priority 3: Reach Range | The opening of the paper towel dispenser is 50" high. Recommendation: Reposition dispenser with opening no higher than 48". (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:42 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 200
66 | 3E | Priority 3: Benches | The bench does not have a clear floor space at the end for a side transfer. Recommendation: Install an accessible bench with a 30x48 clear floor space at the end for side transfer. (Note: If the bench was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:43 | open | Issue | A1 | Women's Dressing Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 2000
67 | 2H | Priority 2: Reach Range | The shelf above the clothes rod is 51-3/4" high. Recommendations: Lower a portion of rod and shelf to a maximum height of 48". (Note: If this shelf was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:45 | open | Issue | A1 | Men's Dressing Room | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:37
68 | 3E | Priority 3: Benches | The bench does not have a clear floor space at the end for a side transfer. Recommendation: Install an accessible bench with a 30x48 clear floor space at the end for side transfer. (Note: If the bench was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:47 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 2000
69 | 3W | Priority 3: Water Closets | The water closet is centered approximately 18-1/2" from the side wall. Recommendation: Reposition the water closet with the centerline 16" to 18" from side wall. (Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:49 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 2500
70 | 3G | Priority 3: Grab Bars | The grab bars at the water closet are positioned with the top of the bar 36-1/2" high. The side grab bar has a clearance of less than 12" between the bar and the toilet paper dispenser Recommendation: Reposition grab bars 33" to 36" to the top of the gripping surface with a minimum 12" clearance above and 1 1/2" below. (Note: If the grab bars and dispenser were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:50 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 400 |  |  |  | Oct 14, 2019 @ 16:40
71 | 3W | Priority 3: Water Closets | The water closet has 48" of clear floor space width measured from the side wall to the edge of the lavatory. Recommendation: Enlarge restroom to allow a full 60" wide clearance at the water closet measured from side wall to edge of lavatory. (Note: If the water closet and lavatory were installed prior to March 15, 2012, they may enjoy safe harbor until modified or replaced.) | May 14, 2021 @ 11:51 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 15000
72 | 3R | Priority 3: Reach Range | The opening of the paper towel dispenser is 50" high. Recommendation: Reposition dispenser with opening no higher than 48". (Note: If the dispenser was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 14, 2021 @ 11:52 | open | Issue | A1 | Men's Dressing Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 200
73 | 2D | Priority 2: Doors | The door has a 49" wide side approach on the pull side. Doors with closers require a minimum 54" side approach width. Recommendation: Remove door closer. | May 14, 2021 @ 11:54 | open | Issue | A1 | Men's Dressing Room | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 150 |  |  |  | Oct 14, 2019 @ 16:57
TOTAL | [16 empty] | 130350

## Downtown_Plaza_Bandstand
Task # | Stamp | Title | Description | Date | Status | Type | Sheet | Location | Created By | Assigned To | # Photos | Color | Archived | Start Date | Due Date | Cost Impact | Cost Impact Amount | Schedule Impact | Schedule Impact Amount (days) | List | Last Updated | Closed On
1 | 2A | Priority 2: Accessible Routes | No accessible route is provided to the bandstand. Recommendation: Install a platform lift. | May 10, 2021 @ 19:00 | open | Issue | C1 | Bandstand | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 12000 |  |  |  | Oct 14, 2019 @ 16:34
2 | 2A | Priority 2: Accessible Routes | No accessible route is provided to fountain or memorial plaques. Recommendation: Install a ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | Fountain | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 10000 |  |  |  | Oct 14, 2019 @ 16:38
4 | 1C | Priority 1: Curb Ramps | Both ramps and landing have excessive cross slopes ranging from 3.3% to 3.7%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | Northwest Curb Ramp | kgoss@abyd.com |  | 8 | red | No |  |  | Yes | 6000 |  |  |  | Oct 14, 2019 @ 17:03
5 | 1A | Priority 1: Accessible Routes | Entire perimeter sidewalk has cross slopes up to 5.6% and excessive changes in level. Recommendation: Remove and replace sidewalk. 584’ x 3’ (1752 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Perimeter Sidewalk | kgoss@abyd.com |  | 13 | red | No |  |  | Yes | 17520 |  |  |  | Oct 14, 2019 @ 16:39
6 | 1A | Priority 1: Accessible Routes | The route from the perimeter sidewalk to the bandstand stairs has running slope of up to 6.9%. Recommendation: Replace sidewalk. (75 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Sidewalk to Bandstand Stairs | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 750 |  |  |  | Oct 14, 2019 @ 16:38
7 | 1C | Priority 1: Curb Ramps | The right-hand ramp and landing have a cross slope ranging from 2.6% to 3.4%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C2 | Southeast Curb Ramp | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 6000 |  |  |  | Oct 14, 2019 @ 16:34
8 | 1A | Priority 1: Accessible Routes | The sidewalk around the bandstand has cross slopes ranging from 2.5% to 5.8% and openings greater than 1/2". Recommendation: Remove and replace sidewalk. (480 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Bandstand Perimeter Sidewalk | kgoss@abyd.com |  | 17 | red | No |  |  | Yes | 4800 |  |  |  | Oct 14, 2019 @ 16:38
9 | 4D | Priority 4: Drinking Fountains | The single drinking fountain is accessible, but no standing height fountain is provided. Recommendation: Install a second fountain with the spout 38" to 43" high. | May 10, 2021 @ 19:00 | open | Issue | C2 | Drinking Fountain | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 3750 |  |  |  | Oct 14, 2019 @ 16:36
10 | 1A | Priority 1: Accessible Routes | The sidewalk to and around the fountain has a cross slope ranging from 2.7% to 8%. Recommendation: Remove and replace sidewalk. (600 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Fountain Perimeter Sidewalk | kgoss@abyd.com |  | 16 | red | No |  |  | Yes | 6000 |  |  |  | Oct 14, 2019 @ 16:38
11 | 1A | Priority 1: Accessible Routes | The route from the perimeter sidewalk to the back of the bandstand has multiple changes in level greater than 1/2". Recommendation: Replace sidewalk. (75 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Sidewalk to Rear Bandstand | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 750 |  |  |  | Oct 14, 2019 @ 16:37
12 | 1A | Priority 1: Accessible Routes | The south sidewalk has an abrupt change in level of 1/2" at the perimeter sidewalk. Recommendation: Grind edge to a 1:2 slope. | May 10, 2021 @ 19:00 | open | Issue | C3 | South Sidewalk to Memorial | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:34
13 | 1A | Priority 1: Accessible Routes | The sidewalk from the north perimeter sidewalk has a running slope of up to 8.3% and changes in level in excess of 1/2". Recommendation: Remove and replace sidewalk. (75 SF) | May 10, 2021 @ 19:00 | open | Issue | C3 | North Sidewalk to Memorial | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 750 |  |  |  | Oct 14, 2019 @ 16:41
14 | 1A | Priority 1: Accessible Routes | The sidewalk around the memorial has cross slopes ranging from 2.5% to 3.5% and excessive gaps and changes in level. Recommendation: Remove and replace sidewalk. (660 SF) | May 10, 2021 @ 19:00 | open | Issue | C3 | Memorial Perimeter Sidewalk | kgoss@abyd.com |  | 23 | red | No |  |  | Yes | 6600 |  |  |  | Oct 14, 2019 @ 16:36
15 | 2P | Priority 2: Protruding Objects | The north side of the sidewalk around the memorial has low tree branches with an overhead clearance of only 70". Recommendation: Trim tree branches. | May 10, 2021 @ 19:00 | open | Issue | C3 | Memorial Perimeter Sidewalk | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:36
16 | 2A | Priority 2: Accessible Routes | The north corner of the sidewalk has a cross slope of approximately 2.4% Recommendation: Remove and replace sidewalk. (100 SF) | May 10, 2021 @ 19:00 | open | Issue | C3 | Memorial Interior Sidewalk | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 1000 |  |  |  | Oct 14, 2019 @ 16:35
17 | 2P | Priority 2: Protruding Objects | The route from the perimeter sidewalk to the back of the bandstand has low tree branches with an overhead clearance of only 74". Recommendation: Trim tree branches. | May 10, 2021 @ 19:00 | open | Issue | C2 | Sidewalk to Rear Bandstand | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 500
18 | 1A | Priority 1: Accessible Routes | The two connecting decomposed granite paths are not stable or firm and have excessive changes in level. Recommendation: Replace route with paved sidewalk. (40 SF) | Jun 24, 2021 @ 13:54 | open | Issue | C2 | Fountain Perimeter Sidewalk | kgoss@abyd.com |  | 8 | red | No |  |  | Yes | 1000
TOTAL | [16 empty] | 78120 |  |  |  | Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:35
Oct 14, 2019 @ 16:35
Oct 14, 2019 @ 16:37
Oct 14, 2019 @ 16:42
Oct 14, 2019 @ 16:36
Oct 14, 2019 @ 16:41
Oct 14, 2019 @ 17:01
Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:42
Oct 14, 2019 @ 16:39
Oct 14, 2019 @ 16:42
Oct 14, 2019 @ 16:41
Oct 14, 2019 @ 16:39
Oct 14, 2019 @ 16:41
Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:37
Oct 14, 2019 @ 16:35
Oct 14, 2019 @ 16:33
Oct 14, 2019 @ 16:39
Oct 14, 2019 @ 16:37
Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:57

## Public_Library
Task # | Stamp | Title | Description | Date | Status | Type | Sheet | Location | Created By | Assigned To | # Photos | Color | Archived | Start Date | Due Date | Cost Impact | Cost Impact Amount | Schedule Impact | Schedule Impact Amount (days) | List | Last Updated | Closed On
1 | 1P | Priority 1: Parking | The three accessible spaces and access aisles facing the building have running slopes of 2.7% to 4.4%. Recommendation: Replace asphalt surface. | May 10, 2021 @ 19:00 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com |  | 8 | red | No |  |  | Yes | 10000 |  |  |  | Oct 14, 2019 @ 16:35
4 | 1P | Priority 1: Parking | The two accessible spaces and access aisle across the drive have a running slope of 2.6% to 3.8%. Recommendation: Replace asphalt surface. | May 10, 2021 @ 19:00 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 6500 |  |  |  | Oct 14, 2019 @ 16:37
6 | 1C | Priority 1: Curb Ramps | The landing and both runs of the parallel curb ramp have a cross slope ranging from 3.2% to 4%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com |  | 11 | red | No |  |  | Yes | 5000 |  |  |  | Oct 14, 2019 @ 16:35
7 | 1A | Priority 1: Accessible Routes | Sidewalk has a 1" gap between panels. Recommendation: Fill gap with caulking material. | May 10, 2021 @ 19:00 | open | Issue | C3 | Route from East Parking | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 100 |  |  |  | Oct 14, 2019 @ 16:34
9 | 1P | Priority 1: Parking | The northernmost accessible space has an uneven surface and a cross slope of approximately 2.8%. Recommendation: Replace asphalt paving and restripe. | May 10, 2021 @ 19:00 | open | Issue | C2 | West Parking Lot | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 3000 |  |  |  | Oct 14, 2019 @ 16:42
10 | 1C | Priority 1: Curb Ramps | The landing and both runs of the parallel curb ramp have a cross slope ranging from 3.1% to 4.9%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C2 | West Parking Lot | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 5000
11 | 1A | Priority 1: Accessible Routes | The sidewalk has a cross slope of to 4.6% and changes in level of up to 1-3/4" in two locations. Recommendation: Remove and replace length of sidewalk. (4panels, 132 SF) | May 10, 2021 @ 19:00 | open | Issue | C2 | Route to Book Drop | kgoss@abyd.com |  | 10 | red | No |  |  | Yes | 1320 |  |  |  | Oct 14, 2019 @ 16:38
12 | 1A | Priority 1: Accessible Routes | The route connecting to the public sidewalk has a cross slope of approximately 2.5%. Recommendation: Remove and replace sidewalk. (25 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | May 10, 2021 @ 19:00 | open | Issue | C1 | West Route from Public ROW | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 250 |  |  |  | Oct 14, 2019 @ 17:03
13 | 1C | Priority 1: Curb Ramps | The curb ramp at the west driveway has a cross slope of approximately 4.8%. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | West Route from Public ROW | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 2500
14 | 1C | Priority 1: Curb Ramps | The parallel curb ramp at the west end of the circle drive has running slopes of 9 and 9.7% on each side. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | West Route from Public ROW | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 5000 |  |  |  | Oct 14, 2019 @ 16:40
15 | 1A | Priority 1: Accessible Routes | The sidewalk has a cross slope of approximately 3.1%. Recommendation: Remove and replace sidewalk. (1 large panel, 120 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 1200 |  |  |  | Oct 14, 2019 @ 16:39
16 | 1A | Priority 1: Accessible Routes | The route connecting to the public sidewalk has a cross slope of approximately 7.5%. Recommendation: Remove and replace sidewalk. (25 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 250 |  |  |  | Oct 14, 2019 @ 16:38
17 | 1C | Priority 1: Curb Ramps | The curb ramp at the east driveway has a cross slope of approximately 2.7% and a 3/4" change in level at the bottom. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 2500 |  |  |  | Oct 14, 2019 @ 16:35
18 | 1C | Priority 1: Curb Ramps | The parallel curb ramp at the east end of the circle drive has excessive cross slopes on both runs and the landing and excessive running slopes on the right-hand run. Recommendation: Remove and replace curb ramp. | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com |  | 10 | red | No |  |  | Yes | 5000
19 | 1A | Priority 1: Accessible Routes | The sidewalk around the tree has a cross slope of up to 3.1%. Recommendation: Remove and replace sidewalk. (2 panels, 96 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com |  | 6 | red | No |  |  | Yes | 960 |  |  |  | Oct 14, 2019 @ 16:34
20 | 1Z | Priority 1: Loading Zones | The covered vehicular area at the Book Drop has a cross slope of approximately 5.7%. Recommendation: Remove and replace paving in this area to ensure a maximum slope of 2% in all directions. Stripe access aisle. (260 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Book Drop | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 3500 |  |  |  | Oct 14, 2019 @ 16:41
23 | 1A | Priority 1: Accessible Routes | A portion of sidewalk leading to the reading garden has a cross slope of approximately 3.1%. Recommendation: Remove and replace sidewalk. (One panel, 42 SF) | May 10, 2021 @ 19:00 | open | Issue | C1 | Route to Reading Garden | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 420 |  |  |  | Oct 14, 2019 @ 16:38
24 | 4D | Priority 4: Drinking Fountains | One accessible drinking fountain is provided, but no standing height fountain is provided. Recommendation: Install a standing height fountain with the spout outlet 38" to 43" high. | May 10, 2021 @ 19:00 | open | Issue | A1 | Restroom Foyer | kgoss@abyd.com |  | 1 | red | No |  |  | Yes | 3750
25 | 3M | Priority 3: Mirrors | The mirror is mounted with the bottom of the reflective surface 48-1/2" high. Recommendation: Install a mirror with the bottom of the reflective surface 40" high maximum. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 300
26 | 3B | Priority 3: Baby Changing Stations | The baby changing table has a rim height of 37”. Recommendation: Modify the table to have a maximum height of 34". | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 3500
27 | 3P | Priority 3: Protruding Objects | The hand dryer protrudes 6-1/2" at 39" high. Recommendation: Relocate hand dryer. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 500
28 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible stall has only 6” of clearance past the latch on the pull side. And no door pull is installed on the inside of the stall door. Recommendation: Swing door inward. Install door pull. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 450
29 | 3W | Priority 3: Water Closets | The centerline of the water closet is 18-1/2" from the side wall. Recommendation: Reposition water closet with the centerline 16" to 18" from the wall. (Note: If the water closet was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 2500
30 | 3G | Priority 3: Grab Bars | The grab bars are installed with the top of the gripping surface 36-3/4" high, and the side grab bar has only 6" of clearance above the bar. Recommendation: Reposition grab bar with the top of the gripping surface 33" to 36" high. Relocate toilet paper dispenser below grab bar. (Note: If these elements were installed prior to March 15, 2012, this condition may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 600
31 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible stall has only 6” of clearance past the latch on the pull side. No door pull is installed on the inside of the stall door, and the door is not self-closing. Recommendation: Swing door inward. Install door pull. Adjust hinges. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:39
32 | 3G | Priority 3: Grab Bars | The grab bars are installed with the top of the gripping surface 36-1/2" high, and the side grab bar has only 6" of clearance above the bar. Recommendation: Reposition grab bar with the top of the gripping surface 33" to 36" high. Relocate toilet paper dispenser below grab bar. (Note: If these elements were installed prior to March 15, 2012, this condition may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 600
33 | 3M | Priority 3: Mirrors | The mirror is mounted with the bottom of the reflective surface 48-3/4" high. Recommendation: Install a mirror with the bottom of the reflective surface 40" high maximum. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 300 |  |  |  | Oct 14, 2019 @ 16:41
34 | 3P | Priority 3: Protruding Objects | The hand dryer protrudes 6-1/2" at 39" high. Recommendation: Relocate hand dryer. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 500
35 | 3B | Priority 3: Baby Changing Stations | The baby changing table requires a reach of 52-1/2" to open and is located within the required maneuvering area of the door. (Please note that TDLR considers baby changing stations to be protruding objects in their open position where the bottom of the table is more than 27" high. In this instance, the table obstructs the door maneuvering clearance in the open position.) Recommendation: Relocate baby changing station outside of the door maneuvering area and position with the handle no higher than 48". | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 450
36 | 2B | Priority 2: Tables | The computer tables are 24-3/4" high and have a knee space height of 23-1/4". Recommendation: Install at least one computer station with a counter height of 26-30" and a knee space height of 24" minimum for children's use. | May 10, 2021 @ 19:00 | open | Issue | A1 | Children's Library | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:42
37 | 4V | Priority 4: Vending Machines | The vending machines have card swipes positioned 59" and 65" high. Recommendation: Replace vending machines. | May 10, 2021 @ 19:00 | open | Issue | A1 | Vending | kgoss@abyd.com |  | 6 | red | No |  |  |  | Unspecified
38 | 2H | Priority 2: Reach Range | The coffee bar counter is 36” high. Recommendation: Lower the counter to 34" high maximum to allow reach to self-serve elements. | May 10, 2021 @ 19:00 | open | Issue | A1 | Coffee Bar | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 3500 |  |  |  | Oct 14, 2019 @ 16:41
39 | 2B | Priority 2: Tables | The round tables throughout the stacks area do not have accessible toe space depth below. Recommendation: Install at least one accessible table. | May 10, 2021 @ 19:00 | open | Issue | A1 | Stacks | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:39
40 | 2B | Priority 2: Tables | Booth tables do not have adequate toe clearance for a forward approach. Recommendation: Install at least one accessible booth table. | May 10, 2021 @ 19:00 | open | Issue | A1 | Teen Area | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 450 |  |  |  | Oct 14, 2019 @ 16:42
41 | 2C | Priority 2: Counters | The charging station counter is 43" high. Recommendation: Modify a portion of the counter to a maximum height of 34". | May 10, 2021 @ 19:00 | open | Issue | A1 | Stacks | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 7500
43 | 2C | Priority 2: Counters | The catalog computers are located on a 41-1/2" high counter with no knee and toe space. Recommendation: Relocate at least one computer to an accessible table. | May 10, 2021 @ 19:00 | open | Issue | A1 | Catalog Computers | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 450
44 | 2C | Priority 2: Counters | The self-serve library card sign-up station has a counter height of 38-1/2". Recommendation: Lower the counter to 34" high maximum with compliant knee and toe space below. | May 10, 2021 @ 19:00 | open | Issue | A1 | Library Card Sign Up | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 450
45 | 1A | Priority 1: Accessible Routes | The accessible route from the public sidewalk across the east drive way has a cross slope of approximately 3.3%. Recommendation: Replace asphalt along this route. (100 SF) | Jun 25, 2021 @ 09:49 | open | Issue | C1 | East Route from Public ROW | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 1000 |  |  |  | Oct 14, 2019 @ 16:36
46 | 1A | Priority 1: Accessible Routes | A portion of sidewalk leading to the reading garden has a 1/2" abrupt change in level. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 10:07 | open | Issue | C1 | Route to Reading Garden | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:38
47 | 1A | Priority 1: Accessible Routes | The sidewalk has a 1/2" abrupt change in level between panels. Recommendation: Grind edge to a maximum 1:2 slope. | Jun 25, 2021 @ 10:15 | open | Issue | C1 | Route to Reading Garden | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:37
51 | 2A | Priority 2: Accessible Routes | Sidewalk has a cross slope of up to 2.6%. Recommendation: Remove and replace sidewalk. (1 panel, 72 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 10:34 | open | Issue | C1 | Reading Garden | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 720
52 | 2A | Priority 2: Accessible Routes | Sidewalk has a cross slope of up to 2.6%. Recommendation: Remove and replace sidewalk. (1 panel, 72 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 10:36 | open | Issue | C1 | Reading Garden | kgoss@abyd.com |  | 2 | red | No |  |  | Yes | 720 |  |  |  | Oct 14, 2019 @ 17:01
53 | 2A | Priority 2: Accessible Routes | Sidewalk has a 1/2" abrupt change in level between panels. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 10:37 | open | Issue | C1 | Reading Garden | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 200
54 | 2A | Priority 2: Accessible Routes | Sidewalk has a cross slope of up to 2.7%. Recommendation: Remove and replace sidewalk. (3 panels, 168 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 10:39 | open | Issue | C1 | Reading Garden | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 1680 |  |  |  | Oct 14, 2019 @ 16:40
55 | 2A | Priority 2: Accessible Routes | Sidewalk has three locations with an approximate 1" gap between panels. Recommendation: Fill gaps with caulking material. | Jun 25, 2021 @ 10:40 | open | Issue | C1 | Reading Garden | kgoss@abyd.com |  | 5 | red | No |  |  | Yes | 300
56 | 1P | Priority 1: Parking | Of the 9 accessible parking spaces provided, only one is designated as a van space. Recommendation: Add a van designation sign to at least one more space in either the east or west lot with an overall width of 16' (8'/8' or 11'/5'). | Jun 25, 2021 @ 10:44 | open | Issue | C3 | Parking - General | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 100
57 | 1A | Priority 1: Accessible Routes | Route has an approximate 1/2" abrupt change in level at joint. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 10:53 | open | Issue | C3 | Route from East Parking | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:34
58 | 1A | Priority 1: Accessible Routes | Route has an approximate 1/2" abrupt change in level at joint. Recommendation: Grind edge to a maximum 1:2 bevel. | Jun 25, 2021 @ 11:00 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:41
59 | 1A | Priority 1: Accessible Routes | Sidewalk has a 1" gap between panels. Recommendation: Fill gap with caulking material. | Jun 25, 2021 @ 11:03 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 100 |  |  |  | Oct 14, 2019 @ 16:36
60 | 1A | Priority 1: Accessible Routes | The covered approach to the main entrance has a cross slope of up to 2.7%. Recommendation: Remove and replace sidewalk. (2 large panels, 160 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | Jun 25, 2021 @ 11:11 | open | Issue | C1 | Route from West Parking | kgoss@abyd.com |  | 4 | red | No |  |  | Yes | 1600 |  |  |  | Oct 14, 2019 @ 16:36
61 | 1P | Priority 1: Parking | The vertical sign at the southernmost accessible parking space is mounted with the bottom of the sign less than 60" high. Recommendation: Reposition sign. | Jun 25, 2021 @ 11:16 | open | Issue | C2 | West Parking Lot | kgoss@abyd.com |  | 3 | red | No |  |  | Yes | 100 |  |  |  | Oct 14, 2019 @ 16:36
62 | 1P | Priority 1: Parking | The vertical parking signs at the three spaces facing the building are mounted less than 60" to the bottom. Recommendation: Reposition signs with the bottom at least 60" high. | Jun 25, 2021 @ 11:31 | open | Issue | C3 | East Parking Lot | kgoss@abyd.com |  | 7 | red | No |  |  | Yes | 300
TOTAL | [16 empty] | 87270
Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:37
Oct 14, 2019 @ 16:35
Oct 14, 2019 @ 16:33
Oct 14, 2019 @ 16:39
Oct 14, 2019 @ 16:37
Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:57

## Westside_Community_Center
Task # | Stamp | Title | Description | Date | Status | Type | Sheet | Location | Created By | Assigned To | # Photos | Color | Archived | Start Date | Due Date | Cost Impact | Cost Impact Amount | Schedule Impact | Schedule Impact Amount (days) | List | Last Updated | Closed On
1 | 2A | Priority 2: Accessible Routes | No accessible route is provided to the stage or vending machines. Recommendation: Install a platform lift for access to the stage. | May 10, 2021 @ 19:00 | open | Issue | A1 | Stage |  |  | 3 | red | No |  |  | Yes | 10000 |  |  |  | Oct 14, 2019 @ 16:34
2 | 4V | Priority 4: Vending Machines | The card slide at the vending machine is 54” high. Recommendation: Replace vending machine. | May 10, 2021 @ 19:00 | open | Issue | A1 | Stage |  |  | 4 | red | No |  |  |  | Unspecified |  |  |  | Oct 14, 2019 @ 16:38
3 | 2P | Priority 2: Protruding Objects | The bleeding control kit projects 10" at 45" high. Recommendation: Relocate or add cane barrier below. | May 10, 2021 @ 19:00 | open | Issue | A1 | Lunchroom Corridor |  |  | 2 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 17:03
4 | 2D | Priority 2: Doors | Door has only 16” of clearance past the latch on the pull side. Recommendation: Modify door configuration to provide a minimum 18" clearance past the latch. | May 10, 2021 @ 19:00 | open | Issue | A1 | Lunchroom/Classroom |  |  | 4 | red | No |  |  | Yes | 2750 |  |  |  | Oct 14, 2019 @ 16:39
5 | 2P | Priority 2: Protruding Objects | Drinking fountains project approximately 7" from the base at 28-1/2" and 32" high. Recommendation: Lower accessible fountain so the bottom of the apron is exactly 27", and install an apron to the high fountain. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator Lobby |  |  | 7 | red | No |  |  | Yes | 3700 |  |  |  | Oct 14, 2019 @ 16:38
6 | 2P | Priority 2: Protruding Objects | The defibrillator box projects 7-1/2" at 48" high. Recommendation: Relocate box or install a partially recessed model. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator Lobby |  |  | 5 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:34
7 | 2C | Priority 2: Counters | The kitchen serving counter is 35” high. Recommendation: Modify at least a portion of counter to a maximum 34" height. | May 10, 2021 @ 19:00 | open | Issue | A1 | Lunchroom Corridor |  |  | 4 | red | No |  |  | Yes | 3500 |  |  |  | Oct 14, 2019 @ 16:38
8 | 3D | Priority 3: Doors | Restroom entry door has only 51” of side approach clearance. Recommendation: Modify toilet partitions to provide a full 54". | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 3 | red | No |  |  | Yes | 1250 |  |  |  | Oct 14, 2019 @ 16:36
9 | 3L | Priority 3: Lavatories | The lavatory has a rim height of 35" and no knee space below. Recommendation: Reconfigure lavatory with rim 34" high maximum and knee and toe space for a forward approach. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 6 | red | No |  |  | Yes | 1750 |  |  |  | Oct 14, 2019 @ 16:38
10 | 3P | Priority 3: Protruding Objects | The paper towel dispenser projects 9" at a 47" high. Recommendation: Relocate dispenser. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 4 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:37
11 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is mounted 53" high. Recommendation: Install hook at a maximum height of 48". (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 2 | red | No |  |  | Yes | 50 |  |  |  | Oct 14, 2019 @ 16:34
12 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing and does not have a pull on the inside. Recommendation: Adjust door hinges. Install door pull. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 2 | red | No |  |  | Yes | 325 |  |  |  | Oct 14, 2019 @ 16:41
13 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is centered 4" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 2 | red | No |  |  | Yes | 225 |  |  |  | Oct 14, 2019 @ 16:36
14 | 3G | Priority 3: Grab Bars | The rear grab bar in the wheelchair accessible toilet stall has only 1" of clearance below the bar. Recommendation: Reposition bar to 1-1/2" above toilet tank. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 3 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:36
15 | 3B | Priority 3: Baby Changing Stations | The baby changing station requires a side reach height of 51" to open and has a surface slope of approximately 7.5% within the clear floor space. Recommendation: Replace baby changing station and locate it where the floor is level and outside of circulation paths. TDLR requires baby changing stations to be considered in their open position when considering protruding objects. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 9 | red | No |  |  | Yes | 1000 |  |  |  | Oct 14, 2019 @ 16:35
16 | 3H | Priority 3: Showers | The accessible shower is not equipped with a handheld shower wand (missing), and the knob adjustment requires tight grasping and twisting of the wrist. Recommendation: Install a compliant handheld shower assembly. | May 10, 2021 @ 19:00 | open | Issue | A1 | Women's Restroom |  |  | 3 | red | No |  |  | Yes | 600
17 | 3D | Priority 3: Doors | Restroom entry door has only 53” of side approach clearance. Recommendation: Modify toilet partition to provide a full 54". Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 4 | red | No |  |  | Yes | 1250
18 | 3P | Priority 3: Protruding Objects | The paper towel dispenser projects 9" at a 47" high. Recommendation: Relocate dispenser. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 4 | red | No |  |  | Yes | 500 |  |  |  | Oct 14, 2019 @ 16:40
19 | 3L | Priority 3: Lavatories | The lavatory has a rim height of 35" and no knee space below. Recommendation: Reconfigure lavatory with rim 34" high maximum and knee and toe space for a forward approach. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 4 | red | No |  |  | Yes | 1750 |  |  |  | Oct 14, 2019 @ 16:35
20 | 3R | Priority 3: Reach Range | The coat hook in the wheelchair accessible toilet stall is mounted 53" high. Recommendation: Install hook at a maximum height of 48". (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 2 | red | No |  |  | Yes | 50
21 | 3C | Priority 3: Toilet Compartments | The door to the wheelchair accessible toilet stall is not self-closing and does not have a pull on the inside. Recommendation: Adjust door hinges. Install door pull. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 2 | red | No |  |  | Yes | 325 |  |  |  | Oct 14, 2019 @ 16:35
22 | 3G | Priority 3: Grab Bars | The rear grab bar in the wheelchair accessible toilet stall has only 1" of clearance below the bar. Recommendation: Reposition bar to 1-1/2" above toilet tank. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 3 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:37
23 | 3W | Priority 3: Water Closets | The toilet paper dispenser in the wheelchair accessible toilet stall is centered 4" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 2 | red | No |  |  | Yes | 225 |  |  |  | Oct 14, 2019 @ 16:42
24 | 3H | Priority 3: Showers | The accessible shower is not equipped with a handheld shower wand (missing), and the knob adjustment requires tight grasping and twisting of the wrist. Recommendation: Install a compliant handheld shower assembly. | May 10, 2021 @ 19:00 | open | Issue | A1 | Men's Restroom |  |  | 2 | red | No |  |  | Yes | 600
25 | 2D | Priority 2: Doors | Two sets of double doors have vision panels positioned with the bottom of the glass 44" high. Recommendation: Replace doors with ones have vision panels positioned with the bottom no more than 43". (Note: If the doors were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Gymnasium |  |  | 4 | red | No |  |  | Yes | 3000 |  |  |  | Oct 14, 2019 @ 16:36
26 | 2P | Priority 2: Protruding Objects | Alarm panel box projects 5" from the wall at 52" high. Recommendation: Provide cane barrier below. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator Lobby |  |  | 4 | red | No |  |  | Yes | 500
27 | 2E | Priority 2: Elevators | The emergency alarm button is centered 31" high. Recommendation: Relocate panel with alarm button 35" high minimum. | May 10, 2021 @ 19:00 | open | Issue | A1 | Elevator |  |  | 2 | red | No |  |  | Yes | 1000 |  |  |  | Oct 14, 2019 @ 16:41
28 | 2D | Priority 2: Doors | Vision panels in 4 doors have the bottom of the glass positioned 45-1/2" high. Recommendation: Replace doors with ones have vision panels positioned with the bottom no more than 43". (Note: If the doors were installed prior to March 15, 2012, they may enjoy safe harbor until replaced.) | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Corridor |  |  | 6 | red | No |  |  | Yes | 3000
29 | 2P | Priority 2: Protruding Objects | The high drinking fountain projects approximately 7" from the base at 33" high. Recommendation: Install an apron to the high fountain to bring the bottom to no more than 27" high. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Corridor |  |  | 4 | red | No |  |  | Yes | 300 |  |  |  | Oct 14, 2019 @ 17:01
30 | 3D | Priority 3: Doors | The door has a side approach width of only 40-1/2". Recommendation: Install automatic door opener. Alternatively, replace lavatory with a more shallow fixture, swing door outward and remove closer. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom |  |  | 4 | red | No |  |  | Yes | 4000
31 | 3R | Priority 3: Reach Range | Coat hook is mounted 68" high. Recommendation: Install a coat hook no higher than 48". | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom |  |  | 3 | red | No |  |  | Yes | 50 |  |  |  | Oct 14, 2019 @ 16:40
32 | 3L | Priority 3: Lavatories | Lavatory drainpipes do not have insulation. Recommendation: Install pipe insulation kit. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom |  |  | 1 | red | No |  |  | Yes | 200
33 | 3W | Priority 3: Water Closets | Water closet is centered 18-1/2" from side wall and seat height is only 16". Recommendation: Replace water closet and install with centerline 16" to 18" from wall. Ensure seat height of 17" to 19". (Note: If this element was installed prior to March 15, 2012, the centerline dimension may enjoy safe harbor until replaced. Add a thicker seat to achieve a height of 17" to 19".) | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom |  |  | 5 | red | No |  |  | Yes | 2625 |  |  |  | Oct 14, 2019 @ 16:42
34 | 3G | Priority 3: Grab Bars | The side grab bar is only 36" long and extends only 48" from the rear wall. Recommendation: Replace with a minimum 42" long grab bar extending 54" from the back wall. | May 10, 2021 @ 19:00 | open | Issue | A1 | Upstairs Women's Restroom |  |  | 4 | red | No |  |  | Yes | 285 |  |  |  | Oct 14, 2019 @ 16:39
35 | 2H | Priority 2: Reach Range | Coat hooks are positioned 66" high. Recommendation: Install at least one hook no higher than 48". | May 10, 2021 @ 19:00 | open | Issue | A1 | Library |  |  | 4 | red | No |  |  | Yes | 50 |  |  |  | Oct 14, 2019 @ 16:42
36 | 1P | Priority 1: Parking | All 4 accessible parking spaces and access aisles have running slopes ranging from 4.3% to 5.9% and a crack in the asphalt. Recommendation: Remove and replace asphalt in this area. | May 11, 2021 @ 19:00 | open | Issue | C2 | Parking Lot |  |  | 12 | red | No |  |  | Yes | 13500
37 | 1A | Priority 1: Accessible Routes | Sidewalk has a cross slope of approximately 2.6%. Recommendation: Remove and replace sidewalk. (1 panel, 30 SF) Note: Due to the relatively low severity of the issue, this correction may be considered low priority. | May 11, 2021 @ 19:00 | open | Issue | C2 | Route from Public ROW |  |  | 3 | red | No |  |  | Yes | 300
38 | 1A | Priority 1: Accessible Routes | A portion of the sidewalk has a cross slope of up to 2.7%, excessive gaps and excessive change in level. Recommendation: Remove and replace sidewalk. (2 panels, 50 SF) | May 11, 2021 @ 19:00 | open | Issue | C2 | Route from Accessible Parking |  |  | 11 | red | No |  |  | Yes | 500
39 | 1A | Priority 1: Accessible Routes | The route has an approximate 1" gap on each side of the metal coverplate. Recommendation: Add caulking material. | Jun 28, 2021 @ 10:22 | open | Issue | C2 | Route from Public ROW |  |  | 4 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:41
40 | 1A | Priority 1: Accessible Routes | Sidewalk has approximate 1" wide openings between panels in two locations. Recommendation: Add caulking material. | Jun 28, 2021 @ 10:23 | open | Issue | C2 | Route from Public ROW |  |  | 7 | red | No |  |  | Yes | 200
41 | 1A | Priority 1: Accessible Routes | Sidewalk has approximate 1" wide openings between panels in two locations. Recommendation: Add caulking material. | Jun 28, 2021 @ 10:54 | open | Issue | C2 | Route from Accessible Parking |  |  | 7 | red | No |  |  | Yes | 200
42 | 3W | Priority 3: Water Closets | The toilet paper dispenser is centered 4" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 13:53 | open | Issue | A1 | Upstairs Women's Restroom |  |  | 2 | red | No |  |  | Yes | 225
43 | 3W | Priority 3: Water Closets | The paper towel dispenser overlaps the 60" wide clear floor space at the water closet. Recommendation: Relocate paper towel dispenser outside of required water closet clearance. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 13:53 | open | Issue | A1 | Upstairs Women's Restroom |  |  | 4 | red | No |  |  | Yes | 200 |  |  |  | Oct 14, 2019 @ 16:39
44 | 3D | Priority 3: Doors | The door has a side approach width of only 39-1/2". Recommendation: Install automatic door opener. Alternatively, replace lavatory with a more shallow fixture, swing door outward and remove closer. | Jun 28, 2021 @ 14:04 | open | Issue | A1 | Upstairs Men's Restroom |  |  | 4 | red | No |  |  | Yes | 4000
45 | 3R | Priority 3: Reach Range | Coat hook is mounted 68" high. Recommendation: Install a coat hook no higher than 48". | Jun 28, 2021 @ 14:07 | open | Issue | A1 | Upstairs Men's Restroom |  |  | 3 | red | No |  |  | Yes | 50
46 | 3L | Priority 3: Lavatories | Lavatory drainpipes do not have insulation. Recommendation: Install pipe insulation kit. | Jun 28, 2021 @ 14:08 | open | Issue | A1 | Upstairs Men's Restroom |  |  | 1 | red | No |  |  | Yes | 200
47 | 3W | Priority 3: Water Closets | Water closet has a seat height of only 16", and the flush is mounted on the wall side of the fixture. Recommendation: Replace water closet. | Jun 28, 2021 @ 14:09 | open | Issue | A1 | Upstairs Men's Restroom |  |  | 3 | red | No |  |  | Yes | 1000 |  |  |  | Oct 14, 2019 @ 16:41
48 | 3W | Priority 3: Water Closets | The paper towel dispenser overlaps the 60" wide clear floor space at the water closet. Recommendation: Relocate paper towel dispenser outside of required water closet clearance. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 14:18 | open | Issue | A1 | Upstairs Men's Restroom |  |  | 3 | red | No |  |  | Yes | 200
50 | 3G | Priority 3: Grab Bars | The side grab bar is only 36" long and extends only 48" from the rear wall. Recommendation: Replace with a minimum 42" long grab bar extending 54" from the back wall. | Jun 28, 2021 @ 14:20 | open | Issue | A1 | Upstairs Men's Restroom |  |  | 4 | red | No |  |  | Yes | 285
51 | 3W | Priority 3: Water Closets | The toilet paper dispenser is centered approximately 5" from the front of the water closet. Recommendation: Reposition dispenser with centerline 7" to 9" in front of water closet. (Note: If this element was installed prior to March 15, 2012, it may enjoy safe harbor until replaced.) | Jun 28, 2021 @ 14:21 | open | Issue | A1 | Upstairs Men's Restroom |  |  | 2 | red | No |  |  | Yes | 225
TOTAL | [16 empty] | 68045
Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:37
Oct 14, 2019 @ 16:35
Oct 14, 2019 @ 16:33
Oct 14, 2019 @ 16:39
Oct 14, 2019 @ 16:37
Oct 14, 2019 @ 16:40
Oct 14, 2019 @ 16:57