| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction Kickoff |  | DATE: | 09/16/2022 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 Meeting discussions points are shown in bold text |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| General Project |  | - Intro and Team Members-Brittney Davis is new POC with Raba Kistner’s ENV team as Sam Blanco is no longer with RKCI: bdavis@rkci.com - Status of Administrative Documents - AFA- Drafted AFA has been submitted to TxDOT. MPO call for projects [Oct] has been paused to due to recent letting overruns. Pause may allow additional funds for future funded projects. If AFA is signed/project is let, no additional funding will be provided. Pause on AFA may result in additional funds being available. AFA is critical path for TxDOT processes (DCC, ENV, etc.) - Dual logos with County?- Yes include Guadalupe County logo. - County / Others?- No project is 50/50 City/County - Billing-Keep format/process from 8th street invoices - Status report preference items- Typical PD status report is sufficient - Invoice template or preference - Timeline - Survey – Aerial (09/17) 10/2022 - DCC – 11/2022* based on TxDOT’s ability to participate due to AFA status. Aerial, alignment alternative and DSR presented at this conference. - 30% DDRT / Schematic – 01/2023- Full TxDOT schematic, Review process is min 6 weeks. DDRT process is 4 weeks from submission to receiving final TxDOT comments, this review period is sufficient for City of Seguin and Guadalupe County. - 60% DDRT – 05/2023- Following TxDOT procedures may require PDCC (pavement design review) and DSRT (safety review) at the 30% or 60% level. - 90% DDRT – 08/2023 (Hold plans during ROW / Utility)- Shown as 100% in contract, plans ready to let but there will be ~14 month period for ROW acquisition, utility relocations, etc. Certification will not be ready until utilities and ROW are clear. - Final Plans – 12/2024- 4/25 letting, final plans5 months prior to being let. - Funding and Commitments - Budget Presentation $31M - Prelim OPCC $33M - $37M w/escalation - How is ROW calculated |  |  |
| 110 Feasibility Studies |  | - Field reconnaissance - Geotechnical - Pavement alternatives - Proposing only flexible options - Specific material preferences? – City of Seguin has minimums, no standards - General preferences required? - Will need to estimate ESALs / Counts - Pavement Report- Standard TxDOT report - Drilling and site investigations - Borings in 3-4wks; 3 wks for processing draft designs - Traffic Studies - Received counts - Planned analysis / TPP vs Option C vs ESALs- Proceeding with Option C and requesting ESAL’s from Austin - Summary Report - Any template preference? - General Geotechnical Comments - If ground water is hit, monitoring wells needed - Due to drought conditions, ground water will likely be low during the time of borings. Geotechnical Engineer to include recommendation for encountering groundwater during traffic signal installation. - There are areas of high sulfate concentrations in the region but can be spotty. This may impact lime treatment abilities. |  |  |
| 120 ENV / Public Involvement |  | - ENV - TxDOT Coordination - Anticipating a CE- Dependent on acreage of proposed ROW, displaced parcels etc. - NEPA / ECOS - Workplan development / ENV Toolkit- Project team develops workplan and TxDOT uses to upload to ECOS- requires AFA - Determination of 404 Permitting - ENV Coordination - Environmental impacts etc. - What ENV considerations are presently known?- Big Red Barn - Optional Assessments and Schedule - Public Involvement - Planned Meetings- City of Seguin to maintain website throughout - Schematic phase - Design phase - Public meeting processes - ADA, location, etc- Preferred location is Big Red Barn if they are willing to partner and cost is reasonable. Spanish and Spanish materials will be needed. - Approval of outreach materials - ROW acquisition - Schedule and regulatory timelines |  |  |
| 130 ROW Data |  | - ROW - Right of entry update - Could our team support with non-responders? Pinnacle will can run TLO report for owner contact information. City of Seguin will start meeting with non-signers to help gain trust. Pinnacle and CD&P willing to participate. - Two known difficult owners- Continental homes, Charles Urban (previous utility issues). - ROW mapping and deliverables - Schedule Update - City of Seguin to share ROW tracking spreadsheet. Spreadsheet to be hosted on PD SharePoint site. - City of Seguin to order title commitments - General Title discussion: City of Seguin prefers local title company. Appraisal will have to follow TxDOT procedures. - Utility Coordination - Utility layouts - Utility Conflict Matrix – TxDOT Standard - Major petroleum line - NOPC – Preferred template? - Scheduled meetings; need to begin soon - Seguin specific contacts |  |  |
| 131 ROW Acquisition |  | - Uniform Act Requirements - TxDOT Forms? - Appraisal and Title require TxDOT Pre-Approved List Agent- Appraisal will have to be from TxDOT pre-approved list. Pinnacle to send City of Seguin a list of a few appraiser/reviewers for selection. - Preparation and starting? - Development of plan framework - Integrating with Connie Real’s Team - Suggested frequency for regular meetings and coordination- ROW to have separate bi-weekly meetings - Prioritization of problematic parcels - Property owner engagement / Public Involvement blending - Negotiations and timelines - Relocation assistance - Known issue with developer activity- one known, possibility for multiple, developers installing sanitary sewer connections along Cordova Rd. - New developments will be required to dedicate for 120’ ROW per current throughfare plan. - City of Seguin to add all new development info to a folder on SharePoint - There was discussion of the possibility of parallel utility easement and the discussion was led to questions on if this would affect the ENV document type. - Spring Hill water line will need to be treated two ways: still Spring Hill owned, and City of Seguin owned. - Potential for water tower at SH 46- ROW acquisition a part of this project |  |  |
| 150 Survey |  | - No planned discussion points |  |  |
| 160 Roadway Design |  | - Preliminary Geometric Layout - 2 – design alternatives (termini at intersections)- One option to be realignment - ROW constraints / developments - DCC - LG process, DDRT / DSRT: Will met with TxDOT SME’s prior to DDRT - Constraints mapping - Pedestrian and bicycle facilities - Regional expansion considerations - TxDOT RDM governed - City of Seguin has access management guidance - Land owner at SH 123 owns all four quadrants- may open up the ability for realignment and or grade separate share use paths in ROW pinch point. - Guadalupe County stated East side of SH 123 realignment would have to be apart of this project if realignment option is selected. Not supportive of offset intersection. - When ready to let and produce project binder, City of Seguin and Guadalupe County need to provide input on Items 1-9. |  |  |
| 161 Drainage |  | - Data collection and field work - Design criteria and design storm - Hydrology studies and modeling requirements - Existing models - Hydraulic modeling and anticipated design- two bridge class culverts within project limits - HEC-RAS and complex modeling / Hydraulic Data Sheets - Storm drain design and outfalls - Detention requirements-if needed, linear/adject to ROW is preferred - Check impacts 2000’ downstream - Potential for remapping of floodplain/LOMR |  |  |
| 162 Traffic |  | - TPP vs Option C-Proceeding with Option C - Signing – specifics? mounts?- Wedge mounts - Warrants and timing plans; specific templates requested?- TxDOT signals Huber Rd doesn’t meet warrant yet. Ground boxes/conduit to be installed for future signalization - Traffic signal design – TxDOT Standards - Known problem locations- There are TxDOT projects planned at each signal location (SH 46 & SH 123). SH 123 will occur in the near term and SH 46 is further into the future. May be able to install temp/span wire signal at SH 123 to avoid building a permanent signal that would be replaced by TxDOT. SH 46 will likely need to be permanent signal due to unknown/uncertain construction timeline |  |  |
| 163 Misc Design |  | - TCP - Likely quad-phased - Lessons learned - Public Involvement strategy - Consideration needs to be made for school traffic. - SW3P - Constraints and mitigation measures - Development of CPM schedule - Anything specific required from City |  |  |
| 164 SUE |  | - No planned discussion points |  |  |
| Project Management |  | - Bi-weekly status meetings (Transition to weekly once project initiates) - Invoicing - Communication protocols - Next steps |  |  |
| Open Discussion |  |  |  |  |
| ACTION ITEMS: Description |  |  |  |  |