| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction Maverick Meadows Coordination |  | DATE: | 04/24/2023 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 |  |  |  |  |  |
| Attendees: | PD (CoS): Steven Tate, Jake Powell, Julian Garcia PD (Maverick Meadows): Brooke Lindholm |  |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |  |
| Cordova Rd |  | All discussion items are subject to final CoS approval Schedule: - Design; Now through Q1 2024 - Pause for utility relocation and ROW - Final plans/letting Q4 2025/Q1 2026 - Construction schedule pending Scope - Full reconstruction - Expand from 2 to 4 lanes with raised median - Dual shared use paths - Minimum of 120’ ROW |  |  |  |
| Maverick Meadows |  | Project Status - Association with Reinhardt Farms? - No association - Status of site plan? - ROW dedication - Construction plans are approved by the city - ROW has not been dedicated and won’t be until plat recorded - Anticipated construction timeline - BitterBlue (developer) is negotiating contract with home builder - Once contract is in place and BitterBlue proceeds; construction could begin in 4-6 weeks - Construction will begin with utilities, streets, and turn lanes prior to completed plat - Approved TIA; right and left turn lanes required. - Timeline for construction- to be constructed with public infrastructure - Possibility to escrow construction cost to be built with Cordova project - BitterBlue may agree to this but would require MOU to ensure no future delays would occur based on TIA requirements that would no longer be valid. - Ultimate design may include one full access driveway due to driveway proximity and access management - Utilities - Connecting to existing 12” water main - Constructing proposed Sanitary sewer within ROW dedication and crossing south to Waters Edge |  |  |  |
| ACTION ITEMS & TAKEAWAYS: Description |  |  |  |  |  |
| - PD (CoS) to brief city on meeting and request construction plans - PD (CoS) and CoS to discuss possible turn lane funding agreements and MOU |  |  |  |  |  |