| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction GVEC Coordination |  | DATE: | 05/4/2023 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 |  |  |  |  |  |
| Attendees: | See Sign-In Sheet Discussion items are shown in bold |  |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |  |
| Cordova Rd |  | Schedule: - Design; Now through Q1 2026- Subject to change - Pending AFA finalization- letting is targeted for Q1 2026 - Construction schedule pending Scope - Full reconstruction from SH 46 to SH 123 - Expand from 2 to 4 lanes with raised median - Dual shared use paths - Minimum of 120’ ROW Design - Project is currently in the early stages of design - Vetting alignment alternatives and seeking stakeholder input - Alternatives are not solidified at this time due to unknown environmental and schedule impacts - Environmental and schedule impacts to be determined with TxDOT participation |  |  |  |
| GVEC |  | Substation near SH 123 - Current operations - There are existing large underground copper circuits that parallel Cordova and cross in multiple locations - Main underground duct consists of 15-4” conduits. 3 circuits with 2 spares - Most of the underground facilities are located in private easements - Duct is not concrete encased - Duct is installed 5’-7’ deep - Significant fiber also present in easements - OHE is double circuit from substation, west, to Huber - Operational challenges - Large mobile substation vehicle - Traffic control generally needed for vehicle - Upcoming plans for the property - Substation is currently at ultimate footprint for long term plan - GVEC may add circuit and transformer in future but would not require expansion Other discussion items - Impacts to substation would be very costly and impactful - Station is main power source for manufacturing operations - Alternative alignment produces less challenges for GVEC - Some local access would be maintained through existing alignment if realignment occurs. - GVEC is experiencing long lead times (1 year+) on copper - When planning for OHE pole relocations; 2-3 degree bend will require concrete pole for double circuit locations - OHE poles have attachements (ATT/Spectrum are known) - Travis Engler will be POC for utility coordination - Utility coordination kickoff meeting to likely occur in August timeframe after TxDOT participation and DCC. |  |  |  |
| ACTION ITEMS & TAKEAWAYS: Description |  |  |  |  |  |
| - GVEC to send mobile substation vehicle information - PD to request maps of underground infrastructure - Beginning utility coordination early will be key to meeting utility clear date (letting). - GVEC prefers the alternative that realigns Cordova Rd to the south of the substation |  |  |  |  |  |