|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **MEETING TITLE:** | City of Seguin – Cordova Rd Reconstruction  TxDOT LG Kickoff | | **DATE:** | 05/16/2023 | |
| **PROJECT NUMBER:** | 12775-00 | |  |  | |
| **AGENDA TOPICS:** | | | | |
| General Project | | 1. Intro and Team Members    1. City of Seguin- Mary Hamann, Pablo Martinez    2. Guadalupe County- Clay Forister    3. TxDOT- Chip Perry, John Bryant, Eddie Gonzales    4. PD- John Tyler, Jake Powell, Steven Tate    5. RKCI- Brittney Davis 2. Background    1. CSJ- 0915-46-052    2. AFA- Executed    3. Project Limits       1. Cordova Rd from SH 46 to SH 123 in City of Seguin/Guadalupe County (~3.4 mi)       2. MPO Description- Expand roadway from 2 to 4 lanes with raised median or center turn lane. Realign Cordova at SH 46. Add shared use paths “on both sides.” 3. Timeline    1. Survey – Complete    2. DCC – 6/1/2023       1. KMZ, typicals, DSR    3. 30% DDRT / Schematic – 7/2023    4. 60% DDRT/DSRT – 11/2023    5. 90% – 03/2024 (Hold plans during ROW / Utility)    6. Final Plans – 06/2025 4. Funding and Commitments    1. Federal- $17,804,902    2. Local- Overage | | |
| Design/ENV / Public Involvement | | 1. Roadway alignment progress    1. Developed roadway alternatives    2. Conducted geometric workshop with CoS and County    3. Reduced alternatives to two options- KMZs    4. Conducted general coordination meetings with large highly affected stakeholders- Texas Agricultural Education & Heritage Center and GVEC.       1. Both stakeholders prefer realigning road around GVEC substation 2. ENV    1. TxDOT coordination to kickoff    2. ECOS initiation    3. Goal is to keep clearance as CE       1. Option 1 (around GVEC)– 32.68 AC       2. Option 1B (around GVEC with misc triangles)- 39.40 AC       3. Option 2 (existing alignment)- 29.51 AC          1. Potential 4F impact    4. Surrounding land is primarily agricultural    5. Displacements and impacts to platted lots are minimized 3. TxDOT Project Coordination    1. SH 46- Received 60% schematic files, CoS issued public comment    2. SH 123- Received files | | |
| Traffic and Geotechnical | | 1. Traffic Studies    1. Option C projections complete    2. Traffic analysis complete    3. Sent Scott Nelson draft memo- ready for review    4. ESAL request from Austin to be made after memo finalized 2. Geotechnical    1. Geotech field investigation, lab testing, and pavement report complete    2. Estimated ESALs for pavement design    3. Ready for PDCC if necessary for off system | | |
| Utilities | | 1. Have identified utility owners within project limits 2. QL B/C/D complete with utility base file 3. Outreach and UCM development to begin | | |
| Open Discussion | |  | | |
| **ACTION ITEMS:**  **Description** | | | | |
|  | | | | |