| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction TxDOT LG Kickoff |  | DATE: | 05/16/2023 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| General Project |  | - Intro and Team Members - City of Seguin- Mary Hamann, Pablo Martinez - Guadalupe County- Clay Forister - TxDOT- Chip Perry, John Bryant, Eddie Gonzales - PD- John Tyler, Jake Powell, Steven Tate - RKCI- Brittney Davis - Background - CSJ- 0915-46-052 - AFA- Executed - Project Limits - Cordova Rd from SH 46 to SH 123 in City of Seguin/Guadalupe County (~3.4 mi) - MPO Description- Expand roadway from 2 to 4 lanes with raised median or center turn lane. Realign Cordova at SH 46. Add shared use paths “on both sides.” - Timeline - Survey – Complete - DCC – 6/1/2023 - KMZ, typicals, DSR - 30% DDRT / Schematic – 7/2023 - 60% DDRT/DSRT – 11/2023 - 90% – 03/2024 (Hold plans during ROW / Utility) - Final Plans – 06/2025 - Funding and Commitments - Federal- $17,804,902 - Local- Overage |  |  |
| Design/ENV / Public Involvement |  | - Roadway alignment progress - Developed roadway alternatives - Conducted geometric workshop with CoS and County - Reduced alternatives to two options- KMZs - Conducted general coordination meetings with large highly affected stakeholders- Texas Agricultural Education & Heritage Center and GVEC. - Both stakeholders prefer realigning road around GVEC substation - ENV - TxDOT coordination to kickoff - ECOS initiation - Goal is to keep clearance as CE - Option 1 (around GVEC)– 32.68 AC - Option 1B (around GVEC with misc triangles)- 39.40 AC - Option 2 (existing alignment)- 29.51 AC - Potential 4F impact - Surrounding land is primarily agricultural - Displacements and impacts to platted lots are minimized - TxDOT Project Coordination - SH 46- Received 60% schematic files, CoS issued public comment - SH 123- Received files |  |  |
| Traffic and Geotechnical |  | - Traffic Studies - Option C projections complete - Traffic analysis complete - Sent Scott Nelson draft memo- ready for review - ESAL request from Austin to be made after memo finalized - Geotechnical - Geotech field investigation, lab testing, and pavement report complete - Estimated ESALs for pavement design - Ready for PDCC if necessary for off system |  |  |
| Utilities |  | - Have identified utility owners within project limits - QL B/C/D complete with utility base file - Outreach and UCM development to begin |  |  |
| Open Discussion |  |  |  |  |
| ACTION ITEMS: Description |  |  |  |  |