| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction Project Coordination |  | DATE: | 06/12/2023 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 |  |  |  |  |  |
| Attendees: | PD: Steven Tate, John Tyler Pinnacle Group: Daniel Shaw CDNP: Jacqie Wilson RKCI: Brittney Davis |  |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |  |
| Project Status |  | Updates - AFA executed, TxDOT participating. - Completed TxDOT DCC, progressing to 30% DDRT and schematic design - Purpose of this meeting is to coordinate PI, ENV, ROW processes and timelines Design schedule - DDRT – 30% Schematic July 13th, 2023 - Public meeting (August 14- Mid September) - DDRT – 60% PS&E November 2023 - 90% PS&E Review March 2024 - Pause for utility relocation and ROW - March 2024 – May 2025 - Final plans/letting Q4 2025 - Construction schedule pending - Letting Nov/Dec 2025 |  |  |  |
| Public Involvement- CDNP |  | Public meeting - Identified August 14th at the earliest - Ideal to hold prior to end of September - PD supplied CoS with additional recommendations and they are determining which options they’d like to include - Next Steps- scheduling/engaging TxDOT - CDNP preparing notices and materials? Details needed? 30 days prior to Public Meeting; Project webpage live on seguintexas.gov. 30 days prior to Public Meeting; Send ALL Public Meeting Notices to TxDOT for Review and Comments. 23 days prior to Public Meeting; Send Meeting Materials to TxDOT for Review. 21 days prior to Public Meeting; Submit an Advertisement to Publication. 17 days prior to Public Meeting; Mail a Public Meeting Notice to Elected Officials. 15 days prior to Public Meeting; Publish Public Meeting Notices on TxDOT Website - this is the ONLY requirement for NEPA compliant notification for a Public Meeting. 14 days prior to Public Meeting; Advertisement is run in Publication. 7 days prior to Public Meeting; Submit Final Meeting Materials to TxDOT for posting. 7 days prior to Public Meeting; Call and Email Community Partners/Organizations. 7 days prior to Public Meeting; Email Campaign 1. 7 days prior to Public Meeting; Distribute Media Release. 3 days prior to Public Meeting; Social Media Post 1. Day of Public Meeting; Post Public Meeting Materials on TxDOT Website. Day of Public Meeting; In-Person/Virtual Public Meeting Live. Day of Public Meeting; Social Media Post 2. 7 days after Public Meeting; Social Media Post 3/Email Campaign 2 – comment period reminder. 14 days after Public Meeting; Social Media Post 4 – final comment period reminder. 15 days after In Person Public Meeting; Official Comment Period Ends. TBD; TxDOT Publishes Final Documentation. |
| ROW- Pinnacle |  | - TROE becoming critical for parcels that will have ROW acquisition - Prepare a map or KMZ that identifies which parcels are missing signed TROE - 89 total ROE letters sent - 65 signed letters received (73%) - 24 ROE letters outstanding Milestones - Signed and Sealed Legal Descriptions Required- - Not started. Need final ROW- 30% design, in planning phase to begin. - Pinnacle would like in Sept/Oct 2023 - Title Commitments - Title Research - We will need the Legal Descriptions for the impacted properties prior to completing this phase - Nov 2023 - Appraisal Inspections/Appraisal Report Completion - By end of Feb 2024 - Appraisal Report Review/City of Seguin Approval of Appraisal - February/March 2024 - Initial Offer Presented - March 2024 - Timeline for PUA/acceptance of offer impacts utility relocation |  |  |  |
| ENV-RKCI |  | - ENV involvement/input needed for public outreach or ROW? TxDOT ECOS initiation - Project descriptions- Sent to TxDOT - Easements/ROW widths/ROW totals - TxDOT Historical review - Meeting tomorrow - RKCI historian preparation TxDOT/NEPA requirements- Schedule impacts? - Air Quality Technical Report and/or Conformity Form - Archeology Background Study (possible survey based on results) - Community Impacts Assessment - Hazardous Materials Initial Site Assessment - Historic PCR (possible survey based on results) - Public Involvement (NOC, maybe public hearing) - Species Analysis Spreadsheet and Form - Surface Waters Analysis Form - Section 404/10 Impacts Table - Waters of the U.S. Delineation - Traffic Noise - Are MAPOs required? |  |  |  |
| ACTION ITEMS & TAKEAWAYS: Description |  |  |  |  |  |