| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction TxDOT Environmental/Historic Items |  | DATE: | 06/13/2023 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| General Project |  | - Attendees - City of Seguin- Pablo Martinez, Melissa Reynolds - Guadalupe County- Clay Forister - TxDOT- Chip Perry, John Bryant, Jennifer Carpenter, Jason Rivas - PD- John Tyler, Steven Tate - RKCI- Brittney Davis - Background - CSJ- 0915-46-052 - AFA- Executed - Project Limits - Cordova Rd from SH 46 to SH 123 in City of Seguin/Guadalupe County (~3.45 mi) - MPO Description- Expand roadway from 2 to 4 lanes with raised median or center turn lane. Realign Cordova at SH 46. Add shared use paths “on both sides.” - ROW- Project will acquire ~40 AC of ROW - Realignment around GVEC substation - Timeline - Survey – Complete - DCC – Complete 6/2023 - 30% DDRT / Schematic – 7/2023 - 60% DDRT/DSRT – 11/2023 - 90% – 03/2024 (Hold plans during ROW / Utility) - Final Plans – 07/2025 - Letting – 11/2025 |  |  |
| Partnership Items |  | - TxDOT branding - ECOS scoping - Team provided WPD1 and WPD2 - ROW AC and Easements - Existing easement acquisition vs proposed permanent easements - Temporary construction easements - Reported 39.8 AC ROW, impacts of adding additional as 30% design is finalized Requesting CE classification - >30 AC |  |  |
| Historic Review |  | - PCR discussion- Jennifer Carpenter - 4F properties - Site visit |  |  |
| Public Involvement |  | - Notice and Opportunity to Comment is minimum required based on current classification - City’s preference is to host public meeting between 30% and 60% design. Current timeline is late August to mid September - Team is preparing notice material for TxDOT review - City is currently reviewing additional email blasts, social media posts, etc - City team to submit notice for review with suggested date ASAP |  |  |
| ACTION ITEMS: Description |  |  |  |  |