|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **MEETING TITLE:** | | City of Seguin – Cordova Rd Reconstruction  CoS Utilities | **DATE:** | 08/11/2023 | |
| **PROJECT NUMBER:** | | 0915-46-052 |  |  | |
| **Attendees:** | | City of Seguin: Pablo Martinez, Terri Ruckstuhl  Pape-Dawson: John Tyler, Jake Powell, Steven Tate, Deepa Elter |  |  | |
| **AGENDA TOPICS:** | | | | |
| Cordova Rd | Project Information   * 1. Cordova Rd from SH 46 to SH 123 in City of Seguin/Guadalupe County (~3.4 mi)   2. Expand roadway from 2 to 4 lanes with raised median or center turn lane. Realign Cordova at SH 46. Add shared use paths “on both sides.”   3. Federal funding      1. TxDOT LG Process   4. Acquiring ~40 AC of ROW. Acquisition taking place on both sides of the road.   Schedule   1. 30% plans complete and submitted 2. 60%- 11/2023 3. 90%-3/2024 4. Pause for ROW and Utility relocations 5. Final plans- 7/2025   Utility Coordination   1. Utility kickoff complete 7/20/23    1. CoS POC needed for the project 2. Following TAC requirements for identification of conflicts and relocations 3. UCM and utility layout complete 4. Requested additional information and review of UCM/layouts from utility owners to be complete by 8/11/23 5. Multiple unresponsive companies, follow-ups and calls being made | | | |
| Utilities | CoS Utilities   1. CoS utility identified within project limits: Sanitary Sewer    1. Conflicts are primarily manhole adjustments    2. Continued review of trunkline depth vs roadway cross sections are on-going   Major conflicts/relocations   1. GVEC 2. AT&T 3. Centerpoint Gas 4. Springs Hill Water 5. Many private easements   Springs Hill Water   1. The team understands the CCN transfer is not complete and will not be until CoS completes multiple projects to supply adequate water. (~2026)    1. Adjustments are the responsibility of Springhill    2. Details need on CoS projects related to Springhill as there may be overlapping project limits and possible conflicts   NORA   1. Utility companies will be requesting language/agreement similar to TxDOTs “Notice of Required Accommodation” (NORA) prior to beginning design    1. NORA protects the utilities if design changes require adjustments to work they have completed.    2. Issue NORA equivalence after 30% comments reviewed and public meeting (October timeframe)   Development   1. Many new developments being proposed along Cordova and surrounding area 2. Review of utility plans/permits?   Other   1. Preference on joint bidding 2. Process for exception requests | | | |