| MEETING TITLE: |  | City of Seguin – Cordova Rd Reconstruction CoS Utilities | DATE: | 08/11/2023 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: |  | 0915-46-052 |  |  |  |
| Attendees: |  | City of Seguin: Pablo Martinez, Terri Ruckstuhl Pape-Dawson: John Tyler, Jake Powell, Steven Tate, Deepa Elter |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| Cordova Rd | Project Information - Cordova Rd from SH 46 to SH 123 in City of Seguin/Guadalupe County (~3.4 mi) - Expand roadway from 2 to 4 lanes with raised median or center turn lane. Realign Cordova at SH 46. Add shared use paths “on both sides.” - Federal funding - TxDOT LG Process - Acquiring ~40 AC of ROW. Acquisition taking place on both sides of the road. Schedule - 30% plans complete and submitted - 60%- 11/2023 - 90%-3/2024 - Pause for ROW and Utility relocations - Final plans- 7/2025 Utility Coordination - Utility kickoff complete 7/20/23 - CoS POC needed for the project - Following TAC requirements for identification of conflicts and relocations - UCM and utility layout complete - Requested additional information and review of UCM/layouts from utility owners to be complete by 8/11/23 - Multiple unresponsive companies, follow-ups and calls being made |  |  |  |
| Utilities | CoS Utilities - CoS utility identified within project limits: Sanitary Sewer - Conflicts are primarily manhole adjustments - Continued review of trunkline depth vs roadway cross sections are on-going Major conflicts/relocations - GVEC - AT&T - Centerpoint Gas - Springs Hill Water - Many private easements Springs Hill Water - The team understands the CCN transfer is not complete and will not be until CoS completes multiple projects to supply adequate water. (~2026) - Adjustments are the responsibility of Springhill - Details need on CoS projects related to Springhill as there may be overlapping project limits and possible conflicts NORA - Utility companies will be requesting language/agreement similar to TxDOTs “Notice of Required Accommodation” (NORA) prior to beginning design - NORA protects the utilities if design changes require adjustments to work they have completed. - Issue NORA equivalence after 30% comments reviewed and public meeting (October timeframe) Development - Many new developments being proposed along Cordova and surrounding area - Review of utility plans/permits? Other - Preference on joint bidding - Process for exception requests |  |  |  |