## Sheet1
Utility Company | Utility Company Contact | Utility Conflict ID | Drawing or Sheet No. | Utility Type | Size and/or Material | Utility Conflict Description | Longitudinal or Crossing | Utility Placement in Relation to Existing TxDOT Right of Way | Station Origin | Start Station | Start Offset | End Station | End Offset | Level of Utility Investigation Needed | Test Hole No. | Test Hole Depth | Recommended Action or Resolution | Estimated Resolution Date | Resolution Status | Comments
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 12 | 2, 5-26 | Water | 8" PVC | Water line | Longitudinal | Outside | Cordova Rd | 112+58 | 520' RT | 293+81 | 40' LT | QLD |  |  | Accommodate - Relocation |  | Utility Conflict Created | Water line conflicts with proposed roadway, row acquisition, proposed drainage and proposed sidewalk. This is an 8" water line.
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 396 | 2, 5-19 | Water | Unknown | Water line | Longitudinal | Outside | Cordova Rd | 112+09 | 590' LT | 248+48 | 36' LT | QLD |  |  | Accommodate - Relocation |  | Utility Conflict Created | Waterline conflicts with proposed roadway and drainage. This is a 16" water line. Facility crosses over Cordova Rd to south side at STA 215+12 and crosses back to north side at STA 227+15
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 406 | 16-26 | Water | 4" PVC | Water line | Longitudinal | Outside | Cordova Rd | 112+09 | 590' LT | 248+48 | 36' LT | QLD |  |  | Accommodate - Relocation |  | Utility Conflict Created | Waterline conflicts with proposed roadway and drainage. This is a 4" water line.
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 192 | 17 | Water | Unknown | Water meter | Longitudinal | Outside | Cordova Rd | 230+47 | 9' RT | 230+47 | 9' RT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Water meter conflicts with proposed roadway
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 207 | 18 | Water | Unknown | Water valve | Longitudinal | Outside | Cordova Rd | 238+31 | 37' LT | 238+31 | 37' LT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Water valve (3) conflicts with row acquisition.
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 160 | 19 | Water | Unknown | Water meter | Longitudinal | Outside | Cordova Rd | 248+29 | 56' RT | 248+29 | 56' RT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Water meter conflicts with proposed roadway
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 235 | 19 | Water | Unknown | Fire hydrant | Longitudinal | Outside | Cordova Rd | 248+31 | 64' RT | 248+31 | 64' RT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Fire hydrant conflicts with proposed driveway
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 236 | 19 | Water | Unknown | Water valve | Longitudinal | Outside | Cordova Rd | 248+34 | 64' RT | 248+34 | 64' RT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Water valve conflicts with row acquisition
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 229 | 19 | Water | Unknown | Water valve | Longitudinal | Outside | Cordova Rd | 248+36 | 34' LT | 248+36 | 34' LT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Water valve (2) conflicts with row acquisition.
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 228 | 19 | Water | Unknown | Fire hydrant | Longitudinal | Outside | Cordova Rd | 248+45 | 33' LT | 248+45 | 33' LT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Fire hydrant conflicts with proposed roadway and driveway
Springs Hill Water Supply Co | Devan Montoya dmontoya@springshill.org | 240 | 19 | Water | Unknown | Fire hydrant | Longitudinal | Outside | Cordova Rd | 254+20 | 30' LT | 254+20 | 30' LT | QLC |  |  | Accommodate - Relocation |  | Utility Conflict Created | Fire hydrant conflicts with proposed roadway and driveway