| MEETING TITLE: |  | Cordova Rd Utility Coordination – SHWSC and City of Seguin Water Improvement Coordination | DATE: | November 7, 2023 |
| --- | --- | --- | --- | --- |
| ATTENDEES: |  | Steven Tate (PD), David Wilder (PD), Erica Keltner (PD), John Tyler (PD), Terri Ruckstuhl (Seguin), Pablo Martinez (Seguin), David Rabago (Trihydro), Nathan Cobler (Kimley-Horn), Clay Forister (Guadalupe County) |  |  |
| AGENDA TOPICS: |  |  |  |  |  |
| - Introductions | - City of Seguin – Terri Ruckstuhl, Pablo Martinez - Guadalupe County – Clay Forister - Trihydro – David Rabago - Kimley-Horn – Nathan Cobler - Pape-Dawson – Steven Tate, John Tyler, Erica Keltner, David Wilder |  |  |  |  |
| - Project Information | - Location and Limits - Seguin, TX - Cordova Rd from SH 46 to SH 123 - Scope: - Widening Cordova Rd from 2 lanes to 4 lanes with raised median - Realign Cordova Rd at SH 46 - Provide shared use path on both sides - Drainage improvements throughout the project area |  |  |  |  |
| - Project Schedule | - 60% PS&E: 11/2023 - 90% PS&E: 3/2024 - 100% PS&E: 7/2025 - Letting Date: 11/2025 |  |  |  |  |
| - ROW Acquisition | - ROW is being acquired through project limits. Minimum ROW will be 120’ |  |  |  |  |
| - Meeting Agenda | - CCN transfer of water line facilities from Springs Hill to the City of Seguin - Discuss on-going city projects related to water improvements - Presence of 3 parallel lines 4”, 8”. and 16”. Springs Hill WSC states that all are active. All information is QLD accuracy as lines are plastic and non toneable. - Condition of existing facilities - Springs Hill WSC has stated all longitudinal installations are 30”-36” deep - TAC regulations require installation of 36” for longitudinal and 60” for crossing - Moving forward - Test holes - Adjustment responsibility - Review Springs Hill WSC conflicts within the project area |  |  |  |  |
| - Questions and Open Discussion |  |  |  |  |  |
| ACTION ITEMS: Description |  |  |  |  |  |

END OF MEMO