| MEETING TITLE: | Lumen Conflict Meeting Agenda |  | DATE: | 11/30/2023 |  |
| --- | --- | --- | --- | --- | --- |
| ATTENDEES: | Steven Tate (PD), David Wilder (PD), Erica Keltner (PD), John Tyler (PD), Ruckstuhl (City of Seguin), Clay Forister (Guadalupe County), Marshall Hollingsworth (Lumen), Nathan Carter (Lumen), David Bryant (Byers, Lumen) |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| 1. Introduction and Project Team |  | - Lumen – Marshall Hollingsworth, Nathan Carter - Byers (for Lumen) David Bryant - City of Seguin – Terri Ruckstuhl - Guadalupe County – Clay Forister - Pape-Dawson - Steven Tate, John Tyler, Erica Keltner, David Wilder |  |  |
| 2. Project Overview |  | - Location and Limits - Seguin, TX - Cordova Rd from SH 46 to SH 123 - Scope: - Widening Cordova Rd from 2 lanes to 4 lanes with raised median - Realign Cordova Rd at SH 46 - Provide shared use path on both sides - Drainage improvements throughout the project area |  |  |
| 3. Schedule |  | - 60% PS&E: 11/2023 - 90% PS&E: 3/2024 - 100% PS&E: 7/2025 - Letting Date: 11/2025 |  |  |
| 4. ROW acquisitions |  | - ROW is being acquired throughout project limits. Minimum ROW will be 120’ |  |  |
| 5. Lumen |  | - Underground conflicts: - All conflicts are underground fiber optics - Conflict ID 175 (Sheet 16) - FOC potentially conflicts with TAC requirements and proposed pavement. - Assumed depth is 2' below existing grade. Ditch cut is 0.5' and pavement section cut is 2' below existing grade. No clearance. - Potential conflict with TAC line does not meet depth requirements and runs longitudinal under proposed Huber Rd pavement. - Conflict ID 338 (Sheet 26) - FOC conflicts with TAC requirements, Culverts F, F-1, and potentially conflicting with proposed pavement. - FOC assumed depth is 2' below existing grade. Culvert F cut is 5.6' below existing grade. Culvert F-1 cut is 3.75' below existing grade. No clearance for either. - Proposed pavement to match existing pavement grade at SH 123. FOC in potential conflict with pavement and TAC depth requirements. - Conflict ID 541 (Sheet 27) - FOC conflicts with TAC and proposed pavement. - Assumed depth is 2' below existing grade. Proposed pavement sections of 2'. No clearance. - FOC runs longitudinally under proposed pavement in conflict with TAC. - FOC in conflict with TAC depth requirements. - Conflict ID 539 (Sheet 27) - FOC conflicts with TAC and proposed pavement. - Assumed depth is 2’ below existing grade. Proposed pavement cuts of 1.3' with pavement sections of 2'. No clearance. Proposed ditch cuts up to 1.4'. Minimal clearance. - FOC runs longitudinally under proposed pavement in conflict with TAC. - FOC in conflict with TAC depth requirements. - Conflict ID 536 (Sheet 27) - FOC conflicts with proposed ditch cuts. - Assumed depth is 2' below existing grade. Proposed ditch cuts up to 1.2'. Minimal clearance. - Conflict ID 540 (Sheet 27) - FOC conflicts with TAC and proposed pavement. - Assumed depth is 2' below existing grade. Proposed pavement sections of 2'. No clearance. - FOC runs longitudinally under proposed pavement in conflict with TAC. - FOC in conflict with TAC depth requirements. |  |  |
| 6. Schedule: Design and Construction timelines |  | - Timeline - Design/Permitting Timeline - Consultant for design? - Construction duration? - Any anticipated long lead times for materials? - Relocate all utilities underground or aerial? |  |  |
| 7. Questions and Open Discussion |  | - Does Lumen concur with placement of existing lines? - Does Lumen concur that all Lumen facilities on Cordova Rd and SH 123 are within the existing ROW? - Can Lumen verify if facilities on Huber Rd crossing Cordova Rd are in a private easement? |  |  |
| ACTION ITEMS: Description |  |  |  |  |