| MEETING TITLE: | AT&T Conflict Meeting Agenda |  | DATE: | 12/12/2023 |  |
| --- | --- | --- | --- | --- | --- |
| ATTENDEES: | Steven Tate (PD), David Wilder (PD), Erica Keltner (PD), John Tyler (PD), Terri Ruckstuhl (City of Seguin), Pablo Martinez (City of Seguin), Clay Forister (Guadalupe County), Parish Austin (AT&T) |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| 1. Introduction and Project Team |  | - AT&T – Parish Austin - City of Seguin – Terri Ruckstuhl, Pablo Martinez - Guadalupe County – Clay Forister - Pape-Dawson - Steven Tate, John Tyler, Erica Keltner, David Wilder |  |  |
| 2. Project Overview |  | - Location and Limits - Seguin, TX - Cordova Rd from SH 46 to SH 123 - Scope: - Widening Cordova Rd from 2 lanes to 4 lanes with raised median - Realign Cordova Rd at SH 46 - Provide shared use path on both sides - Drainage improvements throughout the project area |  |  |
| 3. Schedule |  | - 60% PS&E: 11/2023 - 90% PS&E: 3/2024 - 100% PS&E: 7/2025 - Letting Date: 11/2025 |  |  |
| 4. ROW acquisitions |  | - ROW is being acquired throughout project limits. Minimum ROW will be 120’. |  |  |
| 5. AT&T |  | - Discuss AT&T’s ongoing planning, consolidations, upgrades, etc. - Texas Administrative Code (TAC) noted requirements: - TAC sag height requirement for communication lines is 18’ above roadway. - TAC depth requirement for underground electrical lines is 48” longitudinally and 60” crossing (encased to within 5’ of ROW). - Discuss cabinet/manhole conflicts - Overhead Conflicts - Underground Conflicts - Proposed pavement - Conflict ID 232 (Sheet 19-21) - Proposed drainage improvements - Conflict ID 64 (Sheet 10, Culvert B, Planset Sheet 337) - Discuss Huber Rd facilities - QLB shows AT&T crossing Cordova Rd on west side, but AT&T as-builts do not show lines on the west side of Huber Rd. Can AT&T confirm? - Does AT&T have a private easement for the northwestern property at Huber Rd and Cordova Rd? - Easement impacts and relocations |  |  |
| 6. Schedule: Design and Construction timelines |  | - Timeline - Design/Permitting Timeline - Consultant for design? - Construction duration? - Any anticipated long lead times for materials? |  |  |
| 7. Questions and Open Discussion |  | - Does AT&T concur with placement of existing lines? |  |  |
| ACTION ITEMS: Description |  |  |  |  |